# Preface

The purpose of publishing this Exercise Plan (EXPLAN) is to aid exercise planners and participants in the design of and conduct of the Operation Freedoms Ring Hold Safe Shadow Operation [OFR-HoldSafe] on July 23-24, 2007 in Pasadena, CA.  This EXPLAN also enables participants to understand their roles and responsibilities in exercise planning, execution, and evaluation.

This EXPLAN is tangible evidence of a growing partnership and concern to promote the safety and security of children in the aftermath disasters of all kinds, whether due to natural causes, human error, or acts of terrorism and war.

While most exercises are a culmination of training toward a collective level of preparedness.  OFR-HoldSafe represents an initial step in understanding and demonstrating the special needs presented by children in a disaster event and in exploring how civilians may take protective and productive steps to address these needs in coordination with official civil/military first responders.  This EXPLAN seeks to improve collective readiness by outlining the complex issues that will be addressed through OFR-HoldSafe.

Printed and Current as of:  7/7/2007 3:20 PM

# Administrative Handling Instructions

The title of this document is the Operation Freedoms Ring—Hold Safe Exercise Plan (EXPLAN).

Please do not reproduce this document, in whole or in part, without prior approval from Project K.I.D. or one of the individuals named below.

Lead Full-Scale Exercise Planner Points of Contact:

#### Name			Laramie McNamara

Agency		Highlands Forum – Civilian volunteer

Street Address	9009 Falls Run Road

City, State, Zip	McLean, VA 22102

###### Phone: 		(703) 759-5365

Mobile:		(703) 967-8244

Email: 			lthomara@juno.com

#### Name			Lenore T. Ealy, Ph.D.

Agency		Project K.I.D., Inc.

Street Address	1415 Ironwood Dr. W

City, State, Zip	Carmel, IN 46033

###### Phone: 		(317) 581-0914

Mobile:		(317) 502-2735

Email: 			lenoree@thinkitecture.com

#### Name			Michael C. Berry, Sr.

Agency		Michael C. Berry & Associates, P.A.

Street Address	33 N. Garden Ave., Suite 190

City, State, Zip	Clearwater, FL 33755

###### Phone: 		(727) 447-0533

Mobile:		(727) 403-8661

Email: 			mcberry@berrylaw.com

THIS PAGE INTENTIONALLY LEFT BLANK

TABLE OF CONTENTS

Preface	i

Administrative Handling Instructions	ii

Part 1 – General Information	15

A.	Purpose	15

B.	Definitions & Common Terms	15

C.	Background	16

D.	Exercise Concept and Scope	17

E.	Major Exercise Design Objectives	20

F.	Exercise Scenario	21

G.	Exercise Control and Evaluation	22

H.	Exercise Planning	26

I.	Public Affairs	27

Part 2 – Exercise Participation	29

A.	Exercise Participants	29

B.	Player Rules of Conduct	31

Part 3 – Operations	34

A.	General	34

B.	Briefings and Events	34

C.	Safety	35

Part 4 – Logistics	42

A.	General	42

B.	Security and Access	43

C.	Communications	43

D.	Exercise Communications	44

Appendix A – Schedule of Events	46

Appendix B – Exercise Site Layout	49

Appendix C – VIP/MEDIA INFORMATION	52

Appendix D – SITE REgistration Logistics/FLOW	53

Appendix E – EXERCISE ACTIVITIES	55

Appendix E – EXERCISE RESOURCE SUMMARY	68

THIS PAGE INTENTIONALLY LEFT BLANK

# Part 1 – General Information

## Purpose

This EXPLAN provides planning guidance for the Operation Freedoms Ring—Hold Safe Shadow Operation (OFR-HoldSafe).  This EXPLAN is based on planning factors and estimates available at the time of preparation and is subject to modification during the final exercise planning and preparation.  This EXPLAN will serve as the Controller and Evaluator (C/E) Manual for this exercise, which is designed to help the participating agencies develop more detailed guidance for the conduct of similar exercises in the future.

The EXPLAN is provided to familiarize appropriate agencies with the community’s intent to conduct an interagency exercise, their roles and responsibilities in planning and execution, and the capabilities of the community to respond to the needs of children in all hazards.

OFR-HoldSafe will be conducted on Monday, July, 23, 2007 from 10:00 a.m. until Tuesday, July 14, 2007 at approximately 5:00 p.m.  Multi-agency exercise play is scheduled for both days or until the Exercise Director determines exercise objectives have been accomplished.

## Definitions & Common Terms

For the point of the exercise, the following terminology will be used to identify key areas and personnel:

Exercise Staff/Controllers/Evaluators – Personnel assigned to control the exercise and the exercise artificialities and to evaluate the exercise.

Security – Those persons providing real-world exercise security and access control to the exercise.

Clients – Approximately #30 children will act as “clients” who will be identified and secured at the Child Safety, Security, and Shelter (CSSS) site.  Approximately 50 additional adult personnel will be on site to conduct, observe and evaluate CSSS operations.  The exercise controllers, in conjunction with participating partners, will develop and distribute information materials regarding the role of CSSS operations during a disaster event.

Participants – This EXPLAN applies primarily to participants in the OFR-HoldSafe component of a much larger exercise as well as those persons participating in support of CSSS operations.  For the purposes of this exercise, participants from a multitude of agencies will be participating within a single Incident Command System in order to create an environment for maximum cooperation and collaboration.  This EXPLAN will thus provide instructions and specific guidance for all partnering participants in OFR-HoldSafe.

## Background

Since the onset of the 9/11 and Katrina disasters, everyday civilians have been challenged to respond to the needs of fellow Americans, and to determine appropriate readiness responses in the event of future natural and manmade disasters.  It has become apparent both through disaster exercises such as Strong Angel III, and actual civilian responses to the Katrina disaster, that the unique and specific needs of children have not been adequately addressed in disaster planning.

Following Strong Angel III in San Diego in August 2006, participants in the Highlands Forum began to discuss how civilians (including children) could be empowered to assist in meeting the needs of children during a disaster.  The Highland Forum network ultimately joined forces with the outreach efforts of Project K.I.D..—a spontaneous civilian project created to “hold safe” children during disasters (discussed below)—to create a kids-focused shadow exercise to be played out as a civilian-centric learning experience within Operation Freedoms Ring (OFR).  The exercise will be simply known as OFR-HoldSafe [K.I.D.S.], and its overall objective is to develop best in class techniques that civilians—on the spot at disasters—can implement to organize, to identify, and to provide for the basic needs of children.  These needs include shelter, food and water, ongoing and disaster related medical needs, transport, resolution of legal issues, and family reunification.

Another essential partner in the exercise is the National Center for Missing and Exploited Children (NCMEC).  In the chaotic aftermath of Hurricane Katrina, NCMEC worked to reunify over 5,000 children with their families.  In 2006, In October 2006, Congress and President George W. Bush created the National Emergency Child Locator Center (NECLC). When functioning, NECLC will be operated by NCMEC when a national disaster is declared by the President, to assist in the location of children and the reunification of families resulting from the disaster or subsequent evacuations.

Additionally, the exercise will introduce and demonstrate the Child Safety, Security, and Shelter Site (CSSS), a disaster response asset representing a merger of Project K.I.D.’s PlayCare resource with the concept for a “Children’s Emergency Legal Center” developed in the wake of Katrina by Michael C. Berry, Sr., a Florida attorney who has addressed legal issues of children in disasters, and DMCG, Inc., a Florida-based company that provides disaster mitigation and construction services.

The partners in the exercise find common ground in the conviction that new protocols are needed to guide how children’s needs are addressed during disasters.  Children are known to be resilient, but civilians, first responders and other relief agencies must understand how to create environments even in chaos that encourage resilience.  We must recognize children as individuals having needs quite different from those of adults during a particularly stressful time.

To provide communications, consultation, and support, OFR-HoldSafe will be joined by representatives from Motorola, Verizon, Advanced Wireless Communications, and a variety of other organizations.

## Exercise Concept and Scope

Exercise Concept.  OFR-HoldSafe consists of a tabletop exercise (TTX) and a full-scale exercise.  These two exercises will be used to assess the gaps that exist in first-response systems for children in disaster stress.  They are designed to help develop plans, policies, procedures, protocols, strategies and/or systems that may guide civilian volunteers, first responders and other child-focused response organizations through disasters of all kinds.

OFR-HoldSafe is a Shadow Operation to Operation Golden Phoenix (OGP), a disaster exercise led by U. S. Marine Aircraft Group 46 and joined by over 50 additional civil, military, and civilian agencies.  The exercise will take place on July 23-24, 2007 in Pasadena, CA.  The exercise scenario posits an earthquake event of 8.0 magnitude in the Los Angeles area.  OFR-HoldSafe will extend the scope of OGP by introducing the challenges of the presence of a group of children, including unaccompanied minors, some with preexisting conditions requiring medical care, at the Rose Bowl facility where the field exercise will take place on Tuesday, July 24.

Scope of Play.  The scope of play for the exercise will engage a multi-agency team to simulate the needs of children in the disaster.  Co=located at the Rose Bowl facility with OGP exercises, OFR-HoldSafe will consist primarily in a set of experiments to explore:  (1) how civilian personnel can mobilize in the first days after a disaster to address the emergency needs for child safety, security, and shelter, (2) how civilians can synergistically work with official civil/military first response systems, and (3) what communications and other resources might prove “best of class” for improving  preparedness for and response to children’s needs in future disasters.

In order to effectively pursue these activities within the broader exercise scope of OGP and OFR, OFR-HoldSafe controllers and participants will also seek to operationalize an exercise specific Agency Incident Command System (AICS) to meet the key objectives of the exercise outlined below and will seek to establish communications between this AICS with the Unified Command System that will be established by OGP during the exercise.

Assumptions.  The following general assumptions apply to the exercise:

Badging for access to Rose Bowl site will be provided by OGP and list of participants for OFR-HoldSafe will be provided to OGP.

OFR-HoldSafe is a shadow operation to OGP.  As such, it will seek to minimize dependence on OGP resources and will strive to become an asset on the scene.

With advance notice, OGP will provide access and will accommodate the footprint in the exercise field needed for OFR-HoldSafe assets.

OGP Unified Command will welcome engagement by OFR-HoldSafe personnel and will seek to address critical needs identified, even though these needs present “wrinkles” within the OGP key objectives.  In other words, OGP will be willing to engage with the scenario presented by OFR-HoldSafe.

OFR-HoldSafe will bring to the Rose Bowl site all civilian-centric communications devices, play units, and materials needed to tag and monitor the flow of children and volunteers.

OGP will supply 3 large military tents for use by OFR-HoldSafe, to be erected by military personnel by 0930 on July 24 in the location allocated to OFR-HoldSafe at the exercise site.

Drinking water will be provided by OGP/OFR and OFR-HoldSafe participants will have full access to restroom facilities available during the exercise.

OGP will supply to the OFR-HoldSafe command post 70 meals ready to eat by 1100 on July 24.

Artificialities and Constraints.  The following artificialities and constraints will detract from realism; however, exercise planners and participants accept these artificialities and constraints to facilitate accomplishment of the exercise objectives:

OGP will provide Rose Bowl access and admittance badges to all OFR-HoldSafe participants; names of these participants will be provided to OGP 24 hours prior to the actual conduct of the Rose Bowl exercise.

A maximum of 50 clients, including adults and children will move through the Child Safety, Security, and Shelter Point (CSSS) site.

An additional 25 personnel will be on site participating in or observing CSSS operations.

Participating adult client/volunteers will be assigned an exercise profile to help them prepare for their role in the exercise.

Child clients will carry “symptomology/profile tags” outlining their age, gender, symptoms/injuries, and status for CSSS staff.  These symptomology/profile tags will not take the place of a qualitative client assessment but will rather help to simulate the variety of issues that will emerge around children’s needs in a disaster.

The basic CSSS site footprint will be mapped as part of this document and will be physically established in the first hour of the exercise on Tuesday, July 24.  Military assistance and resources may be provided to simulate the basic footprint of the CSSS.

The exercise will be played in real time.  Some events, however, may require time jumps or may be accelerated to meet exercise objectives.

Additionally, to ensure the safety of children on the scene, the CSSS deployment, including PlayCare site, will be prepositioned before the start of the exercise activities.  In a real disaster, the full-scale CSSS and/or stand alone PlayCare site could be resources requested for mission tasks by Incident Command.

For the field exercise, all staff will be pre-staged at the assembly area at the Rose Bowl parking lot, Pasadena, CA.  Actual response time to this assembly area will not be evaluated.

The Planning and Finance and Administration Sections of ICS will not be activated or operate as part of the exercise.

## Major Exercise Design Objectives

The following design objectives were identified for the multi-agency component of OFR-HoldSafe:

- Introduce kid issues into a major field exercise.  Simply raising awareness of the issues surrounding children with the general public, and first responders, by having children on scene will accomplish a major step forward in disaster response planning and resource development.

- Develop civilian-centric, self-organizing techniques that will assist in addressing the needs of kids.

- Determine the most appropriate organization and use of commonly available civilian portable communications devices; determine guidelines for the best use of available communications equipment in the first 24 hours.

- As appropriate determine the best interfaces for civilian communication, video and information equipment with both child-centric agencies (e.g. NCMEC, Project K.I.D.) as well as civil/military first responders.

- Secure access for civilian communications to civil/military communications so that critical needs and information can get out of the disaster site to potential responding organizations (NCMEC, hospitals, tele-med, tele-judge).

- Assess the viability of a Child Safety, Security, and Shelter Point (CSSS) as a component of first response capabilities:

  - Introduce into the exercise a discrete response resource targeted to the needs of children (CSSS) and establish an Incident Command Structure and rules of engagement with formal civil/military commands.

  - Move children on the scene to a discrete and secure CSSS.

  - Process at least 20 children to gather identification data and assess any medical and/or legal issues.

  - Transmit data on at least 10 unaccompanied minors to the National Center for Missing and Exploited Children’s (NCMEC) locator center.

  - Transmit data on critical medical needs of at least 5 children to responding medical personnel and/or tele-medical resources.

  - Provide medical care for at least 2 children by gaining access to the medical facility established on site during the field exercise.

  - Transmit data and facilitate tele-judicial hearing on legal issues of at least 2 children.

  - Conduct background checks in the field on at least 10 volunteers arriving at the scene to help.  In addition we would like to conduct background checks on at least 5 select Marines from the “angry crowd”.

  - Provide for wellbeing (food, water, shelter, activity) of children assuming that they cannot be evacuated from the scene for up to 72 hours post-event.

Additionally, the following organization-specific objectives were identified by Project K.I.D. :

Assess the ability of Project K.I.D. PlayCare staff to support first responders through evaluation of:

  - PlayCare assembly and staging at the CSSS;

  - Play Care set-up and Just-in-Time Training;  Project K.I.D. will spot-train at least 4 adult volunteers to work with children at the CSSS.

  - PlayCare check in of accompanied and unaccompanied minors.

  - Multi-jurisdictional/multi-agency cooperation between all participating agencies.

## Exercise Scenario

Scenario Confidentiality.  The exercise is an unclassified exercise.  No effort will be made to exercise control over information.  In fact, the point of the exercise is to draw attention to the needs of children in disasters in order to encourage attention to these issues in future exercises and planning activities.

Some exercise material is intended for the exclusive use of exercise planners, controllers, and evaluators; however, players and observers may view all exercise materials.

## Exercise Control and Evaluation

General.  This section describes the exercise control concept and delineates associated responsibilities for the management and control of the exercise.

Concept for Exercise Control.  The scope of play and number of participating agencies will require close cooperation throughout the exercise.  An essential element for the successful conduct of this exercise will be the integration of all exercise participants into a cohesive team that will pursue identified incident objectives.

Exercise Directors.  Overall control will be the responsibility of the Exercise Director(s), Laramie McNamara and Lenore Ealy, who will also serve during this exercise as Incident Commanders.  The Exercise Directors will act as moderators to explain or clarify the physical surroundings during play.  An exercise orientation will be provided to participants during the TTX and Briefing scheduled for Monday, July 23.  Clients/volunteers playing only on July 24 will receive a briefing on site at 1000 at the CSSS.

Control Information Transfer.  A principal method of information transfer for controllers during the exercise within the OFR-HoldSafe component will be via a designated radio frequency on a shared radio system.  Motorola will supply the radios and radio system used during the OFR-HoldSafe exercise.

Figure 1-1.  Rose Bowl-Specific Organization for OFR-HoldSafe

| Incident Command Staff | Incident Commanders Laramie McNamara, External Incident Commander Lenore Ealy, Internal Incident Commander Communications Officer: Jim Bean |
| --- | --- |
|  | Liaison (EAIC) | Public Info (Debbie Baldwin) | Safety (Richard Price ) | Documentation (SRA Personnel) |
| Sections | PLANNING | OPERATIONS | LOGISTICS | FINANCE |
|  | Performed by Incident Command Staff and Operations & Logistics Chief | Michael Berry Paige Ellison Smith | Jim Bean For the exercise all participants will assist in set-up and break-down of exercise site footprint. | Will not be activated for the exercise: (Agencies to cover their own costs.) |

Figure 1-2.  OFR-HoldSafe Operations Section Chart

Command Structure and Responsibilities.  The Exercise Directors will be responsible for the following:

External Agency Incident Commander (EAIC)

  - Acts as OFR-HoldSafe liason between OGP, OFR, and other Rose Bowl on-site players.

  - Acts as first point of contact for all outside civil and military personnel who need to engage OFR-HoldSafe for purposes of the overall exercise.

  - Acts of first point of contact for all VIPs and press seeking access and information on OFR-HoldSafe

  - Works with Internal Agency Incident Commander to coordinate and adjust all scheduling and logistics support exchanged among OGP, OFR and OFR-HoldSafe.

  - The Public Information Officer, Communications Deputy and Liason Officer will be primary support for External Agency Incident Commander.  They will assist in coordination of efforts with the Internal Agency Incident Commander (IAIC). The Communications Deputy will support both EAIC and IAIC.

Internal Agency Incident Commander (IAIC)

  - Monitors exercise progress and coordinating decisions regarding any deviations or significant changes to the scenario caused by unexpected developments during play.

  - Monitors actions by functional area controllers and individual controllers to ensure all appropriate actions are taken to manage an effective exercise.

  - Coordinates any required modifications to the timeline and individual event implementers with the appropriate functional area controller.

  - Stays at the incident site to monitor and observe player and controller activities.

Functional Area Command/Control Structure.

Logistics Section Controller:  The Communications Officer will perform this role.

Registration Controller:  SRA personnel supported by Debbie Baldwin.

CSSS Site Controller/Evaluator:  The Internal Incident Commander will perform this role for the exercise.

Functional area controllers have limited decision making authority in their respective areas.  Any changes that impact the scenario or affect other areas of play must be coordinated through the Exercise Directors.

Exercise Implementation and Rules

Real emergency actions take priority over exercise actions.

“This is a real emergency” will be the designated phrase that indicates there is an emergency in the exercise area requiring immediate attention that may or may not stop exercise play.

Modification or intentional disruption of communication circuits is prohibited.

Exercise players will comply with real-world response procedures unless otherwise directed by controllers.  Player rules of conduct are outlined in Part 2 (Exercise Participation) of this EXPLAN.

All radio communications and telephone conversations made during the exercise will begin and end with the words, “This is an exercise.”

Exercise players placing telephone calls must identify the organization, agency, office or individual with whom they wish to speak.

Exercise Security.  Exercise security is addressed in Part 4 (Logistics) of this EXPLAN.

Exercise Safety.  With children on the scene, safety throughout the exercise is paramount.  Safety issues are detailed in Part 3 (Operations) of this EXPLAN, including procedures for initiating a response to real world emergencies.

Concept of Exercise Evaluation.  The focus of the exercise is to (1) explore how civilian personnel can mobilize in the first days after a disaster to address the emergency needs for child safety, security, and shelter, (2) assess how civilians can synergistically work with official civil/military first response systems, and (3) determine what communications and other resources might prove “best of class” for improving  preparedness for and response to children’s needs in future disasters.   Evaluation will also assess the viability of a Child Safety, Security, and Shelter Point (CSSS) as a model for civilian-centric volunteer efforts and an addition to first response capabilities.  Evaluation and documentation should develop a civilian preparedness model, identify strengths and weaknesses in civilian and first-response awareness, and identify future training needs.  The exercise will focus on agency coordination, communications and critical decisions.  All critical participants will provide an after action evaluation.  Independent evaluators will be positioned at the CSSS to assist in the overall identification of issues.

Evaluators.  Evaluators work as a team with controllers.  They do not interact with players.  Evaluators will record events and ensure documentation is submitted for review and inclusion in the After-Action Report (AAR)/Improvement Plan (IP).  Evaluators will not interfere with the integrity of the exercise or players.  All questions raised during the exercise will be addressed by the controller onsite.

Manuals and Evaluation Forms.  This EXPLAN will be used to guide the conduct and evaluation of the field exercise.

## Exercise Planning

Exercise Planning Responsibilities.  The External and Internal Incident Commanders are jointly responsible for the following:

During exercise planning and design, ensuring all exercise documentation is coordinated thoroughly with all participating organizations.

During the exercise, supervising controller operations, including controller reporting.

Responsibilities.  To successfully fulfill exercise objectives, the exercise planning team will accomplish the following:

Coordinate the exercise, administrative, and technical planning input, including planning conferences conducted to ensure planning milestones are met.

Write, coordinate, and distribute the EXPLAN as well as changes and supplements thereto.

Develop an exercise briefing for presentation that will keep controllers, planners and senior officials in participating agencies informed on the background and status of the exercise.

Collect, consolidate and coordinate exercise evaluation comments for inclusion in an After Action Report/Improvement Plan that will include observations, lessons learned/best practices and recommendations for improvement of response policies and procedures.

Ensure all exercise players have attended player orientation training.

Develop the necessary documentation for the conduct of the exercise; to include a registration list of all those participating in the exercise.

Act as the central point of coordination for the participating planners.

Facilitate and provide input during the Controller/Evaluator Debriefing following the exercise.

Conduct training for exercise players, controllers and evaluators.

## Public Affairs

General.  This exercise offers an opportunity to demonstrate capabilities that might be developed to address the needs of children after an earthquake of 8.0 magnitude in the Los Angeles County Operational Area.  Any public safety exercise of this scope is a newsworthy event.  Because OFR-HoldSafe deals with children, news media attention on the scene can be expected.

Special attention must be given to the needs of the news media, allowing them to get as complete and accurate a story as possible, but ensuring their activities do not impact the realism of the exercise, compromise safety or the exercise objectives.  A Media, Observer, and VIP (MOV) Plan, which provides specific and detailed guidance for the management of MOV, has been prepared as a appendix to this document.

Exercise Responsibilities

Pre-Exercise.  The community is responsible for disseminating public information in advance of the exercise.  This function will be coordinated by OFR-HoldSafe Exercise Directors.

During the Exercise.  Media personnel will only enter the exercise play area with assigned escorts at all times.

See separate APPENDIX

for MEDIA PERSONNEL AND VIPs.

THIS PAGE INTENTIONALLY LEFT BLANK

# Part 2 – Exercise Participation

## Exercise Participants

Players.  Players are multi-agency personnel who will assume an active role in activating and operating the CSSS by performing assigned roles and responsibilities during the exercise scenario.  Players will also include support personnel who may be offsite but have an integral role in facilitating response and action.  For this exercise, exercise players will each be assigned some role in the OFR-HoldSafe (Agency) Incident Command System.

Controllers.  Controllers are exercise participants who plan and manage the exercise play, setup and operate the exercise incident site, and act in the roles of response individuals and agencies not actually playing in the exercise.  Controllers provide key data to players and may prompt or initiate certain player actions to ensure exercise continuity.  For this exercise the controllers are the External and Internal Agency Incident Commanders.  All operations and logistics chiefs are accountable to External and Internal Incident Commanders.

Controllers are the only participants who will provide information or direction to the players.  Controllers may employ compressed time or space to ensure exercise continuity and completion.

Evaluators.  Evaluators are individuals from various agencies chosen to evaluate and comment on designated functional areas of the exercise.  Evaluators have a passive role in the exercise and only note the actions of players; they do not interfere with the flow of the exercise.

Volunteers (aka Clients).  Clients/Volunteers (hereafter, clients) are volunteer participants who simulate specific roles during the exercise play. A client may serve as an evaluator during role play.  OFR-HoldSafe will utilize up to 50 clients, including adults and children.

Observers.  Observers view all or selected portions of exercise play but do not participate in exercise play or in exercise control functions.  Observers may direct their questions to Exercise Directors.

Unified Command Staff.  OFR-HoldSafe is a shadow operation.  One of the objectives of the operation will therefore be to establish rules of engagement (formal or informal) with the OGP Unified Command Staff. OFR-Hold Safe External Incident Commander will serve as liaison to OGP Unified Command Staff.

Table 2-1.  Participating Organizations

| Law Enforcement/Judicial |
| --- |
| California administrative judge? |  |
| Fire/EMS |
| Disaster Response/Mitigation Organizations |
| Project K.I.D. | M.C. Berry Team |
| National Center for Missing & Exploited Children | DMCG, Inc. |
|  | Brethren DCC? To be invited |
| Child-Oriented Agencies (Observers/Volunteers) |
| California Child Care Resource & Referral Network? |  |
| Medical/Public Health |
| Premier |  |
| Norma Hamilton, RN |  |
| Communications |
| Verizon | Advanced Wireless |
| Motorola |  |
| Volunteer Organizations |
| World Cares Center (Orloff) |  |
| Hope Worldwide (to be invited) | Other orgs? Lions, churches, Boy Scouts, Screen Actors Guild |
| Media, Public Information, Other |
| Trojan Vision? |  |

## Player Rules of Conduct

If an actual emergency occurs during the exercise, controllers will immediately suspend exercise play and evaluate the situation.  The Internal Agency Incident Commander will then decide if the exercise can be safely resumed.

The safety and security of children on the scene is the premier consideration during the exercise.  Please notify controllers immediately if there are safety or security concerns with regard to the children.

Act in a professional manner at all times.

Understand the scope of the exercise.  If you are unsure about a certain organization’s or agency’s participation in the exercise, ask a controller.

Do not “fight” the scenario.  Recognize that the exercise has objectives that must be satisfied and may require doing things that may not be as realistic given the natural constraints of an exercise.

Speak out loud when you are taking action.  Recognize controllers and evaluators can only note actions of which they are aware.

Act on all controller instructions; with the exception of safety issues, even if you do not agree with what the controller is telling you, do not argue.  Complete the required actions and make a note to discuss your disagreement at the end of the exercise during the critique.  Remember the controller has the final word.

Do not engage in casual conversations with the controllers.  If you are asked a question, give a short, concise answer.  If you are busy and cannot immediately respond, indicate that, but report back with an answer at the earliest possible time.

Do not engage in conversations with evaluators.  If an evaluator persists in talking to you, ask a controller for assistance.

Maintain a log of your activities, when possible.  Many times, this log may include documentation of activities missed by a controller or evaluator.

Except for the actions identified in the list of actions to be simulated, or as otherwise directed by exercise controllers, respond to exercise events and information as if the emergency were real.

Attend to safety issues at all times.  Observe Security and industrial/health protection controls required by exercise conditions.

Adhere to public laws, including traffic regulations and follow any and all orders given by law enforcement personnel.

OFR-HoldSafe is a shadow operation to OGP.  You are expected to obtain other necessary information through OFR-HoldSafe emergency information channels only. Refrain from communication with OGP players unless specifically directed by controllers to engage with them.  When engaging OGP players, who have other assigned objectives and tasks unrelated to OFR-HoldSafe, focus on your assigned objective and maintain professionalism.

Except for “Real Emergency” notifications and communications that are part of the exercise objective (NCMEC data transfer, telemed, telejudge), participating personnel will simulate radio contact with off-site agencies.

THIS PAGE INTENTIONALLY LEFT BLANK

# Part 3 – Operations

## General

The multi-agency participation of this exercise is expected to span two days or until the External and Internal AICs determine the exercise objectives have been accomplished; this may incline the exercise to run longer than intended.  The actions of participating agencies and players will be in response to events outlined in the Schedule of Events (see Appendix A).  The basis for actions in the field will be a combination of existing agency procedures/capabilities, exercise directives, additional tasks and skills acquired during training.  Therefore, the exercise scenario is limited in scope, serving as a catalyst for initial actions and as a list of projected operational milestones.  The exercise scenario allows the control staff to ensure the exercise stays on track and objectives are met.  The External and Internal AICs may identify additional actions or adjustments required during the exercise to guide play to ensure these objectives are met.

## Briefings and Events

Descriptions of the significant exercise events follow.  Appendix A of this EXPLAN contains a list of exercise events.

Controller and Evaluator Orientation Briefing.  The EXPLAN will be delivered via email or US mail to evaluators approximately one week prior to the exercise.  All Participants are asked to review the manual to familiarize themselves with the EXPLAN and to prepare themselves for performance of their functions.  A controller-evaluator briefing will be conducted on Monday, July 23 14:00 at the Ritz Carlton Pasadena.  Questions should be addressed and information clarified at this briefing so controllers and evaluators feel confident they can effectively perform their assignments.

Client/Volunteer Briefing.  This briefing will be conducted the morning of the exercise at 10:00 at the OFR-HoldSafe intake area at the Rose Bowl parking lot.  The role and importance of the volunteers will be reviewed as well as the details of the symptomology/profile cards, safety issues, and any other information pertinent to their participation.

Exercise Play.  Staff/Player activity will take place on Monday, July 23 from 09:45 to 16:30 at the Ritz Carlton Huntington in Pasadena.  Staff/player activity on July 24 will begin as soon as site access is allowed (projected for 09:00) with the initiation of Play will proceed in accordance with established plans and procedures.  The exercise will conclude at the direction of the Exercise Directors and on the substantial completion of operations and attainment of the exercise objectives.  The exercise is expected to end at approximately 17:00.  A Hot Wash for Controllers, Evaluators and Key Players/Staff will begin at approximately 17:30.

The exercise schedule for the Rose Bowl field exercise on Tuesday, July 24 is detailed in Appendix A of this EXPLAN.  The following are some exercise guidelines:

Registration Controllers will check-in no later than 08:30., evaluators and all other controllers will check in no later than 09:00 (see Appendix A – Schedule of Events) for final instruction.  All controllers must be in their assigned places for the start of the exercise no later than 10:00 on the day of the exercise.

Exercise play will not be halted for player breaks or, where occurring, shift changes.

Player Hot Wash.  This block of time is provided to gather the first impressions of players about exercise conduct and play.  Observers are not encouraged to attend, unless by specific invitation of exercise officials.  Controllers and evaluators are encouraged to attend because they may find the information useful for the completion of controller notes and evaluation forms.  The hot wash will be conducted immediately following the completion of the exercise.

Controller/Evaluator Debriefing.  This debriefing is a forum for representatives to review the exercise.  It will be a facilitated discussion covering each exercise objective and the exercise process.  During the debriefing, controllers and evaluators will have the opportunity to complete and hand in their exercise materials and for discussion to take place among the exercise evaluators, Incident Command staff, station leaders and general staff.  This debriefing will be conducted by conference call within one week of the end of the exercise.

## Safety

All participating organizations recognize the importance of conducting an exercise of this magnitude as safely as possible.

Richard Price will serve as safety controller for the exercise.  The safety controller will have no other duties.

Definitions

Safety Controller.  The safety controller looks out for the safety of all exercise participants.  This person is not responsible for providing controller injects to play activities.  Any real safety concerns should be reported to a controller, who will be Incident Command Staff.  The controller has full authority regarding any safety-related aspect of exercise play.  All participants will follow the safety controller’s directions.

Exercise Controllers.  Exercise controllers help guide the exercise.  They provide exercise injects and information to the players.  All exercise controllers will also serve as safety observers during the exercise.

Exercise Safety Requirements (General).  Participant safety takes priority over exercise events.  Although the organizations involved with the exercise come from various agencies, they share the basic concept of ensuring a safe and healthful workplace for their personnel.  Professional health and safety ethics should guide all participants to operate in their assigned roles in the safest manner possible.  The following general requirements apply to the exercise:

  - All exercise controllers will serve as safety observers while exercise activities are underway.

  - Participants will be responsible to look out for their own and each other’s safety during the exercise.  It is the responsibility of every person associated with the exercise to stop play if, in his or her opinion, a real safety problem exists.  Once the problem is corrected, exercise play can then be restarted.

  - All organizations will comply with their respective environmental, health and safety plans and procedures; as well as all appropriate Federal, State and local environmental health and safety regulations.

Scope.  The exercise presents a potential safety hazard to all participants.  For this reason, an exercise safety controller has been established to identify those hazards and make appropriate recommendations to ensure participant safety at all times.

Medical Support.  If participants need medical support for minor injuries and illnesses during the exercise, medical support will be provided by the OFR-HoldSafe Pediatric Medical Group.  A dedicated medical evacuation support unit will not be available on site during the exercise. If medical evacuation support is needed at anytime during the exercise, controllers will be instructed to dial 9-1-1.

Accident Reporting.  All injuries, incidents and accidents, regardless of severity, will be reported immediately to the nearest controller.  Anyone observing a participant who is seriously ill or injured will first advise the nearest controller and then render first aid, if possible, provided the aid given does not exceed his or her training.

Use of Alcohol.  Alcohol consumption will not be allowed during the exercise.  If a controller detects the presence of alcohol on a participant or if a participant is believed to be under the influence, the controller will remove the participant from the exercise and report the participant to his or her supervisor for appropriate follow-on action.

Illegal Drugs.  The use of illegal drugs is prohibited.  If a controller detects the presence of drugs on a participant or if a participant is believed to be under the influence, the controller will remove the participant from the exercise and report the participant to his or her supervisor for appropriate follow-on action.

Activity-Specific Safety Requirements

Operation Golden Phoenix will maintain access control to the exercise area to ensure unauthorized non-participants are denied access and authorized non-participants transiting the exercise area to reach other work areas do so without deviating from established routes or reasonable travel times.  OGP personnel performing exercise site security are not direct participants in the OFR-HoldSafe exercise and will not be exposed (as part of the exercise) to any scenario-related play.

In an area of exercise pedestrian traffic, drivers will not exceed 5 miles per hour, except in real emergency situations.  Emergency lights for participating units may be employed during the exercise.

Weather Considerations.  The exercise area is the parking lot of the Rose Bowl in Pasadena, California.  Actual weather conditions will be used during the exercise.

Heat Stress.  Heat stress is defined by the following conditions presented in order of increasing severity: heat rash, heat cramps, heat exhaustion, and heat stroke (hot, dry skin).  Ambient temperature, ambient humidity, work activity, and physical fitness/acclimatization of exercise participants mainly influence heat stress.

Heat stress can be controlled by drinking plenty of water (available at the site), avoiding alcohol (before and during exercise), complying with proper work/rest regimens, and maintaining the core body temperature below 100.4 °F.  Controllers are responsible for assessing the exercise participants for heat stress potential and taking prompt corrective action to mitigate dangerous heat stress conditions.

Exercise participants who experience a significant heat stress condition (e.g., heat exhaustion and heat stroke) should immediately stop working, inform a safety controller, and report to the on-site medical players.  Basic response actions for a client of severe heat stress include moving to a shaded location (preferably air conditioned) and administering water.

Hypothermia.  Hypothermia is defined as the progressive cooling of the body.  This cooling can occur rapidly (e.g., when a person is immersed in cold water) or gradually (e.g., through general outdoor exposure in cold weather).  The body can adjust to a drop of a few degrees of internal body temperature, but larger temperature losses can result in the inability of the body to regulate its temperature and produce necessary body heat.  The signs and symptoms of hypothermia include the following:

Shivering (or, in severe cases, the absence of shivering)

Numbness

Drowsiness or inactivity

Stiff or rigid posture

Rapid breathing and pulse at the onset (slow breathing and pulse in severe cases)

Coordination difficulties (e.g., staggering)

Joint/muscle stiffness

Decreased level of consciousness

All exercise participants are susceptible to the effects of hypothermia.  Hypothermia can be controlled by gradually warming the person, giving warm liquids to conscious persons, and keeping the person warm.  All controllers and the safety controller are responsible for assessing exercise participants for cold injury potential and taking corrective action to mitigate dangerous conditions.

Exercise participants who experience cold injuries or the signs and symptoms of hypothermia should immediately stop working, inform a controller, and be brought to the on-scene real emergency site.

Real Emergency Procedures.  For an emergency that requires medical assistance, the phrase will be “This is a Real Emergency.” The following procedures will be used in case of an actual emergency during the exercise:

The first exercise player, controller, evaluator, or observer who becomes aware of an actual emergency will initiate the broadcast of “This is a Real Emergency” over frequencies being used at the exercise.

All radio transmissions will cease, except the unit that first transmitted “This is a Real Emergency” will specify the following information:

  - Location

  - Condition

  - Requirements (if possible)

If requirements at the scene are specified, only those units requested will respond.

If an actual medical emergency occurs, the aided will be immediately removed via the dedicated ambulance, for real emergencies only, to the appropriate receiving medical facility.

If the nature of the emergency is such that a suspension of the exercise is needed, all exercise activities will immediately cease.

Fire Safety.  Dispatch on-scene will be notified and should provide support in case a fire or other emergency occurs during the exercise that is not part of exercise play.  Following are fire safety requirements for the exercise:

Firefighting equipment will be readily available and in close proximity.

Particular care will be taken to ensure no exercise operations cause unintentional fires.

Re-supply fuels, specifically gasoline, kerosene, and diesel fuel, will be stored only in approved containers.  They will be clearly labeled for content and will be stored away from combustible materials.  They will not be stored within 50 feet of an ignition source such as open flames or electrical or gas-operated equipment that could spark or short out.  “No Smoking” signs will be posted near the storage area.  Fire extinguishers and other safety equipment will be stored close to the re-supply fuel storage area, but not with the fuel containers.  Fuels will be handled using safe handling methods.

Weapons Safety.  As participants in a civilian-oriented response exercise, OFR-HoldSafe participants do not require, nor should they possess, weapons during the exercise.

For the purpose of this policy, a weapon shall include all firearms, knives, explosive devices, less than lethal weapons/tools/devices, and any other object capable of causing bodily harm.

Qualified personnel (law enforcement, security, military, etc.) with legal authority to carry weapons that have an assigned exercise role (player, tactical team, etc.) and have the potential for interaction with other exercise participants shall NOT carry a loaded weapon within the confines of the exercise play area.  They may continue to carry their weapon only after it has been properly cleared and rendered safe (i.e., no ammunition in chamber, cylinder, breach, or magazines) and only after being marked or identified in a conspicuous manner (i.e., bright visible tape around the visible stock or holster).  The use of an area clearly marked as “off limits,” and with assigned armed personnel to secure weapons in a container, vehicle, or other security area is acceptable, and should be consistent with host jurisdiction weapons security policies.

Qualified personnel (law enforcement, security, military, etc.) with legal authority to carry weapons that are utilized to provide “real world” perimeter security for the exercise and have no assigned or direct interaction with exercise participants may continue to carry loaded weapons as part of their normal scope of duty.

All other personnel with no legal authority to carry weapons shall not bring, introduce, or have in their possession any weapon of any type in any area associated with the exercise.  Safety briefings will be provided to all exercise participants specifying provisions and policies regarding weapons prior to the start of the exercise.

Aggressive behavior will not be tolerated during exercise conduct, except in matters of self-defense.  Examples of aggressive behavior may include but are not limited to: excessive speeding; uncontrolled animals (i.e. K-9s, horses, etc.); employment of defense products (i.e. mace, pepper spray, stun guns, tasers, batons, etc.); and forceful use of operational response equipment or tools (i.e. pike poles, hose lines used at full stream on clients, etc.).

THIS PAGE INTENTIONALLY LEFT BLANK

# Part 4 – Logistics

## General

This section specifies tasks to accomplish specific support exercise preparation, conduct, and/or evaluation.

Symptomologies/Profiles.  Symptomology/Profile Cards will be developed by OFR-HoldSafe Planners, and will be printed and distributed by the same.  These symptomology/profile cards will have been created to define specific roles of children in each exercise activity.

OFR-HoldSafe Exercise Command Center.  The OFR-HoldSafe Exercise Command Center will be responsible for controlling all aspects of the OFR-HoldSafe element of the exercise to include the exercise evaluation components.

Meals.  Snacks and drinks will be provided for Exercise Participants, Clients and Observers by OFR-HoldSafe; however, lunch will not be provided.  All participants will be encouraged to eat before conduct of the exercise and provide their own sack lunch.

Badging/Access.  All K.I.D.S. Participants, Controllers and Evaluators will be required to wear a badge at all times.

Communications.  Controller communication will be provided through the use of hand-held radios.  Alternative or backup communications for controllers will be through the use of personal cell phones.

Registration Process.  OFR will register all Exercise Participants, Controllers, Evaluators and Clients.  OFR-HoldSafe will compile a list of participants in advance of the exercise, and all exercise participants, controllers, evaluators and clients MUST register and provide the requisite information on exercise day.

Parking.  Parking for exercise participants, controllers, evaluators, observers at Address.  XXX are to park as usual at XXX, XXX, CA.

Staging Areas.  Upon entry to the exercise site, all OFR-HoldSafe personnel and clients will proceed to the OFR-HoldSafe Command Center at the CSSS location.  Children will be accompanied by qualified adults bearing clear identification at all times once they enter the exercise site.   At the “Client Staging Area” at the CSSS client/volunteers will receive their briefing and will subsequently be assigned to their exercise start area.   Exercise controllers, evaluators and security will at the OFR-HoldSafe Command Center.

Restroom Facilities.  Restrooms will be located onsite, and within the Rose Bowl facility, for use during the exercise.

Cleanup and Restoration.  Following the exercise, agencies will begin equipment removal and cleanup operations to restore the area to pre-exercise conditions.  All agencies assist in these efforts by instructing personnel to refrain from littering and to begin removal of equipment and vehicles as soon as possible after the exercise.

## Security and Access

General.  OGP personnel will be assigned to control entry into the selected site and only authorized personnel will be permitted access into the exercise play areas and will be responsible for maintaining the security of the exercise site.

OFR-HoldSafe Staff will assist in traffic control, designated parking and any other security requirements that may arise during preparation or conduct of the exercise.  OGP will notify OFR-HoldSafe if there are special requirements or need for dedicated staff to fulfill these responsibilities.

This is an unclassified exercise; however, participants must take appropriate security measures to safeguard information and material they deem sensitive throughout the exercise.

Responsibilities.  The Exercise Director and exercise planning team are responsible for establishing policies, concepts and standards for the exercise.

Each participating organization should follow its internal security procedures, augmented as necessary, to comply with exercise requirements.

Visitor Coordination.  OFR-HoldSafe Incident Commanders will be responsible for coordinating exercise RSVPs.  Each organization with visitors will coordinate with OFR-HoldSafe Incident Command Staff for access to the exercise site.  In the event that persons attempt to RSVP that are not on the invited lists, OFR-HoldSafe will verify with the primary agencies the appropriateness of their attendance prior to responding.

Exercise Identification.  All Participants and Clients should wear white t-shirts for the field exercise on Tuesday, July 24.

## Communications

OFR-HoldSafe participants will rely primarily upon cell phone communications to simulate reality of civilian response capabilities.

OFR-HoldSafe Agency Incident Command Staff may also have radio communications operating on a separate and specific network.

The OFR-HoldSafe Communications Unit will coordinate player communication networks and channels.

OFR-HoldSafe, in conjunction with the Communications Officer will provide a copy of the Communications guidelines to players in advance of the exercise.

“This is a Real Emergency” will be the designated phrase to indicate there is a real world emergency in the exercise area that requires immediate attention.

## Exercise Communications

All spoken and written communications WITH OFFICIAL AGENCIES will start and end with the statement, “This is an exercise”

Player/Staff Communications.  Players will follow pre-designated OFR-HoldSafe Communications Plans and procedures.

The need to maintain a response capability for real-world response may preclude the use of all communications channels or systems that would usually be available for an actual incident.  In no instance will exercise communications interfere with real-world emergency communications.

Controller Communications.  OFR-HoldSafe will not start the exercise with access to  Controller Communications Radio Network, though this access may be established during the exercise.

Exercise Activation.  The commencement of exercise play will be initiated by the Exercise Director and will be communicated via radio to OFR-HoldSafe controllers from OFR-HoldSafe Incident Commanders.

THIS PAGE INTENTIONALLY LEFT BLANK

# Appendix A – Schedule of Events

| Time | Personnel | Activity | Location |
| --- | --- | --- | --- |
| Monday, July 23, 2007 |
| 9:45 | Core Team Participants | Registration/badging | Ritz Carlton Pasadena |
| 10:00 a.m. | Core Team Participants | Welcome Laramie McNamara & Lenore Ealy | Ritz Carlton |
| 10:15 a.m. | Core Team Participants | Overview, Terms and Conditions of Exercise Dave Warner | Ritz Carlton |
| 10:30 | Core Team Participants | Exercise Background, Player Capabilities Roundtable | Ritz Carlton |
| 11:00 | Core Team Participants | Overview of Scenario, Objectives, Schedule of Events Laramie McNamara & Lenore Ealy | Ritz Carlton |
| 12:00 | Core Team Participants | Breakout TTX Discussions Lunch, Sponsored by Verizon | Ritz Carlton |
| 2:00 | Core Team Participants | Adjourn | Ritz Carlton |
| 2:00 | Controllers/ Evaluators | Controller/Evaluator Briefing | Ritz Carlton |
| Tuesday, July 24, 2007 Pending final alignment with OGP/OFR timelines |
| 08:00 | OFR-HS Incident Command, Operations, and Registration personnel | Pre-staging of OFR-HS resources | Designated area TBD near Rose Bowl Parking |
| 09:00 | OFR-HS Participants | Registration, Site Briefing, and Footprint Setup (CSSS and Comms) | OGP Access Gate and OFR-HoldSafe Footprint TBD |
| 09:30 | OFR-HS Exercise Security-ID group | Comms Set-Up/check. Comms group starts play on Activity 1 as soon as possible | CSSS Comms Center |
| 10:00 | Registration Controllers | Registration of arriving adult/child volunteers | OGP Access Gate |
| 10:00-11:00 | Security-ID Group, Shelter Group, | Activity 2. ID children. Move children to secured CSSS site, | CSSS Intake area |
| 10:00- ENDEX | Shelter and PlayCare Groups | Activities/Lunch/snacks for kids | CSSS Shelter/Recreation area |
| 10:30 | Shelter/Legal, Security-ID Group, Comms Unit | Activity 3. ID adult volunteers Background check all arriving adult clients; assign arriving adult clients to jobs; spot train | CSSS Intake area |
| 11:00 | ALL | Break in all adult activities. Exercise overview and safety briefing with adult volunteers | CSSS Intake area |
| 10:30 | PedMed Group, | Activity 4. Assess symptomology cards for arriving children, provide/obtain needed care | CSSS Medical area |
| 11:00 a.m. | Pediatric Medical Group and Comms Unit | Activity 4 cont. Civilian medical data/comms |  |
| 12:00 | Shelter/Legal, Security-ID Group, Comms Unit | Activity 6 commences. Transmit data to NCMEC for at least 10 arriving “unaccompanied minors” | CSSS Comms Center |
| 1:30 p.m. | Pediatric Medical Task Force/Shelter-ID | Activity 5. Tele-med engagement for needs of 5 children. Obtain medical care for 2 children at on-site OGP medical facility. |  |
| 3:00 p.m. | Shelter/Legal Group, Comms | Tele-judge administrative hearing for 2 children (assuming imminent evacuation of children out of state) |  |
| 4:00 p.m. | Clients | All Adult/Child clients (with exception of those engaged in tele-med or tele-judge activities) to check-out and depart |  |
| 4:00 p.m. | All OFR-HoldSafe Staff | Begin wind-down of CSSS and Comms |  |
| 5:00 p.m. | All | Exercise ends (ENDEX). |  |
| 5:15 p.m.– 5:45 p.m. | Controllers, Evaluators, and Key Exercise Players/ Supervisors | Controller/Evaluator/Key Exercise Player Hot Wash Turn in all Participant Feedback Forms. |  |
| 5:45 p.m.– 6:15 p.m. | Controllers, Evaluators, and Key Players/ Supervisors | Controller/Evaluator Debriefing Turn in all C/E materials and evaluation forms. |  |

# Appendix B – Exercise Site Layout

INSERT EXERCISE SITE MAP WITH EXERCISE AREAS (INCLUDING REGISTRATION, FLOW DIAGRAMS, ETC. INCLUDED)  Attached as separate document.  (Can be attached as separate document.)

Figure B-1:  Aerial View of Rose Bowl Site

Insert Rose Bowl to Ritz Carlton Google Map driving directions here (I could print but couldn’t cut/paste?!)

Insert CSSS footprint here.

# Appendix C – VIP/MEDIA INFORMATION

# Appendix D – SITE REgistration Logistics/FLOW

Time:  At earliest site access time until all volunteers have arrived.

Place:  OGP Exercise Access Gate at Rose Bowl Parking lot

Personnel:

- OFR-Hold Safe Registration Controller (SRA staff/Debbie Baldwin)

- PlayCare Shepherds

- OFR Badge personnel

- OFR-HoldSafe Volunteer Coordinator

Equipment:

Registration sign in sheet (name of each person; signature and name of responsible party; sponsoring organization…)

liability waivers

for adults

for children

adult background check waivers

adult background check information sheets

preliminary badges/safety vests? for kids by color code

symptomology/profile cards

badges for accompanying volunteers

File folder box with folders for each client

Process Flow:

Participants and clients will arrive at Rose Bowl security/access gate for clearance.  At registration, children will be assigned a “symptomology/profile card.”  Once registered and cleared, OFR-HoldSafe volunteers, adults and children, will be shephered by clearly identified OFR-HoldSafe personnel to the OFR-HoldSafe location.  Adults will transport their own registration folder to CSSS Intake.  Shepherds will transport each child’s registration folder to CSSS Intake.

Critical Considerations:

This is an organizational exercise.  Its purpose is to create an inventory of all adult and child volunteers and to assure that any necessary releases are signed and in order.  It will also begin the process of securing children at the disaster site.

For security, shepherds for this exercise will have been identified, trained, tagged and briefed on their roles on Monday, July 23.  No arriving volunteers will be allowed to shepherd.

TTX Issues to Resove:

- Registration/badging will be coordinated with OGP/OFR badging by OFR personnel?

- Can registration of children be done simply with some tracking at this point?

- Can we cross check child badges with accompanying/responsible adult information?

- Will it work to provide symptomology/profile cards at this registration/access point?

- Do we need any unique permissions/waivers for medical/legal child players?

- Check Motorola radios, licensing to determine frequency for HoldSafe

# Appendix E – EXERCISE ACTIVITIES

EXERCISE ACTIVITY 1

ORGANIZE ON SITE CIVILIANS AND CIVILIAN COMMUNICATIONS DEVICES TO GET HELP

Time:	At STARTEX (09:00) to ENDEX

Place:	OFR-HoldSafe Intake/Communications Tent on Rose Bowl OFR-HoldSafe Footprint

Players:

- Adult volunteers

- Verizon communications reps

- Motorola communications reps

- NCMEC representatives

- Ham radio operator

- CSSS Security-ID Operations group

Equipment:

- 2 comms tables

- 8 chairs

- 10 Motorola radio communications devices with pre-determined frequencies

- Motorola provided civilian used cell phones, pdas

- Motorola provided commonly available civilian laptops

- Verizon/Motorola provided wireless internet access for laptops

- Volunteer provided digital and other photo/video equipment

- Ham radio w/operator

Scenario:

A demonstration soccer game is being held at the Rose Bowl.  The Soccer Federation has invited groups of various aged children from elementary, middle, and high schools in Southern California to attend.  Some kids arrive as class groups with teacher and parent chaperones; others come as family units; some teenagers may be at the game without adult supervision; and some children may be attending as part of a vacation trip with various caretakers.

During the event, an 8.0 earthquake hits.  The Rose Bowl facility is damaged and people are evacuated to the parking lots. There is significant damage in surrounding areas that inhibits mass exodus by car.  All attendees who had arrived by MTA Gold Line are stranded without means of private transportation.  Until otherwise notified, the only safe ground is the parking lot area.  [For the purposes of this exercise note that Rose Bowl restroom facilities will be available.]

Adults on the scene will need to determine how to self-organize, with the resources they have on hand and the skills sets they collectively possess, to secure, identify, and tend to the unique needs of children now in their care.

The only power available is that which is left on phones, PDAs, laptops, and other consumer devices, including vehicles, that civilians might bring to a game.  Police, fire, and other first responders are occupied in emergency safety activities and are not available until they specifically seek OFR-HoldSafe out to provide assistance.

Purpose of Activity:

This activity seeks to determine how civilian volunteers can self-organize to effectively determine critical tasks that need to be performed to meet the unique needs of children.  The focus of this task is to determine what civilian communications devices are on hand, can be collected for common use and “the good of the order,” and effectively used to communicate to the “outside world.”  Control of incoming calls should be assessed and managed. (Note that in a real emergency incoming call traffic is frequently blocked.)

This activity should determine and set priorities for the use of civilian communications equipment for:

- Sending calls and data for medical assistance

- Sending calls and data for legal assistance

- Conducting background checks on adults interacting with kids

- Identifying kids, taking pictures, collecting critical information on each child, and transmitting pertinent data on unaccompanied minors to NCMEC.

- Sending calls and data for food, water, shelter, clothing needs

- Transmitting PlayCare needs (to Project K.I.D., Brethren DCC, etc.)

- Dedicated and incoming call lines

Note:  Motorola and Verizon representatives will be available to assist in assessing the use and capacity of various devices for the purposes identified above.  As advisors they will make note of the capacity, use limitations, and unique uses of instruments that civilians might not commonly know.

Process Flow:

As early as site footprint is set up comms teams and the “civilian leadership team” will begin to experiment with civilian communications resources.

The “civilian leadership team” will be comprised of exercise volunteers who have been pre-identified and assigned profile cards describing their role.  There will be civilian profiles for parents, teachers, attorney, nurse, retired law enforcement, day care operator, etc. in the mix.  The “civilian leadership team” will receive a briefing on the scenario and key objectives at the TTX on July 23 and during the TTX will begin to assign roles and responsibilities for the Exercise Activities to be conducted on July 24.  Some roles and assignments will be  pre-designated by the Exercise Directors (see the proposed Incident Command System in the EXPLAN for example).

The “civilian leadership team” may be augmented as play proceeds on July 24 by volunteers arriving that day.

The “civilian leadership team” will be pre-positioned at the OFR-HoldSafe footprint to be assigned in the Rose Bowl parking lot and will begin execution of Exercise Activity 2 in the Intake/Comms area as soon as the footprint is set-up.  As children and other volunteers arrive the team will shift attention to other exercise activities/objectives.

TTX Issues to Resolve

- Is the inventory of civilian electronic devices both representative and an adequate sample of what civilians might have at a stadium event?

- Are there other devices that might be available?

- How will volunteer self-organization interact with technical reps?

- Who sets civilian priorities for helping kids?

- When should volunteer background checks be activated?

- What rules to be set on using comms to contact concerned family?

EXERCISE ACTIVITY 2

IDENTIFY, TAG, SHEPHERD ALL MINOR CHILDREN ON SITE

Time:	10:00 and as children arrive

Place:	OFR-HoldSafe Footprint

Players:

- Adult volunteers

- Motorola id, tag, and track groups

- NCMEC representatives

- Verizon, Motorola and other civilian comms advisors

- CSSS Operations groups (all)

Equipment:

- 1 intake tables

- 4 chairs

- equipment to create and place tags on kids (bracelet or other, color coded, bar coded, tags)

- equipment to read, check, transmit data

- equipment to create hard copy and/or electronically store lists and tracking of processed children

- symptomology/profile cards for children clients

- “INTAKE” forms for children inclusive of NCMEC id and tracking criteria

- Paper, scissors, tape, pens, Ziploc sandwich bags, string

- Civilian technology:.. cell phones, pdas, laptops, digital cameras (still and/or video) (would OnStar equipped vehicle be available?)

Scenario:

All children who were attending a Rose Bowl event when the earthquake occurred have been gathered by adult volunteers together in the OFR-HoldSafe intake area.  Some children are with their parents; others are with a field trip chaperone; some have been left with the children’s group while their parents respond in other ways; several present as unaccompanied minors who have been separated from their families in the disaster.

Some present minor injuries (the assumption is that first response medical teams would be addressing trauma requiring emergency medical attention).  Some will present symptoms of non-emergency conditions that may become life threatening in the hours after the disaster:  asthma, diabetes, wheelchair confinement, etc.

Civilian volunteers, including parents and school chaperones, have recognized the need to secure children in a safe location and have cordoned off an area and are seeking means to engage with first responders to address the needs of children.  They have recognized the urgency of getting data on unaccompanied minors and children with medical conditions out to first responders and NCMEC.

Note:  The CSSS/PlayCare site would likely not be available in these earliest hours post-disaster.  They are serving as pre-positioned assets in order (1) to demonstrate their potential role in disaster response, (2) to ensure the safety and security of children clients in the exercise, (3) to experiment with systems of managing such sites in cooperation with civil/military responders in the future.

Additionally, there will be communications equipment available that would not be immediately available to civilians at a disaster scene.  Nevertheless, attempt will be made in the exercise to accomplish exercise objectives with readily available civilian comms utilizing the most simple, civilian friendly processes.  Meanwhile, demonstration of the capabilities of more sophisticated equipment will play an important role in evaluating how organizations such as schools, child care centers, recreation facilities, and shelters can better prepare to meet children’s needs in future disasters.

Purpose of the Activity:

This activity is designed to begin identifying and inventorying each child on site, discerning the needs of each child, making arrangements for safety, security and shelter (including overnight shelter).

The main focus of this exercise is to determine the critical information to be gathered and transmitted on each child and where that information is best transmitted.  This information should be the basis of the data needed to meet initial needs of children at the scene.  The exercise will also seek to electronically interface and merge with NCMEC call center, medical aid providers (tele-med and on-site), and legal facilitators (tele-judge and on-site).

Key Objectives:

- Process through intake and tag a minimum of 20 children

- Transmit data on at least 10 unaccompanied minors to NCMEC

- Identify 3-5 medical alerts to be addressed

- Identify 2-3 legal special needs to be addressed

- Demonstrate ability to secure all minor children in inner perimeter of CSSS and to ensure that any child processed through intake would be accompanied by an adult shepherd if moved out of the CSSS

- Demonstrate child shelter and PlayCare activities for a minimum of 20 children for the entire exercise day.

Process Flow:

Child Intake:  From access gate/registration shepherds will accompany children to the CSSS “intake” area where Security/ID teams will interview, identify and produce tags for each child (name badge, bracelet, etc?).  ID will involve not only interviewing the child for personal data but also noting special data included on the “symptomology/profile card” each child received at Registration.  Medical staff will begin to assess their needs.

Shelter/PlayCare:  As children are identified and tagged through the Intake process they will proceed with a shepherd into the shelter/PlayCare area where staff will engage them in activities/lunch/snacks.  Children will not leave the inner perimeter without a qualified CSSS Shepherd accompanying them.

Critical Considerations

Liability Waiver:  For each adult and child there will not only be an individual badge/tag created, but also a folder with any release form that must be signed in order to proceed with intake at the CSSS site.

No adult should enter the CSSS inner perimeter without appropriate identification and clearance through OFR-HoldSafe Intake.

No child should be on the exercise site in any location without an identified adult shepherd.

TTX Issues to resolve:

- How do we ID/tag children and adult simultaneously?

- Are there low-tech, workable civilian means of tagging in immediate hours after a disaster?

- Are tags for kids the same type as those for screened adult volunteers?

- What sort of non-transferable, non-duplicable identification might be used for screened adults?

- What are the rules of play for parents/guardians who are not volunteering?  Can they accompany their child?  Must a volunteer escort?

- How will we divide up tests for different/competing ID/tagging solutions?

- Do we need power sources for making and storing information on ID/tags

- How can we conserve power sources and have data readily available over several days?

- What comms that are on site need to play in this process?  How does this fit with the exercise objective to utilize civilian comms to the greatest extent possible?

EXERCISE ACTIVITY 3

IDENTIFY, QUALIFY, TRAIN, and ASSIGN ALL SPONTANTEOUS CIVILIAN VOLUNTEERS

Time:	10:00 and as spontaneous adult volunteers arrive

Place:	OFR-HoldSafe Footprint

Players:

- Adult volunteers

- Motorola id, tag, and track groups

- NCMEC representatives

- Verizon, Motorola and other civilian comms advisors

- CSSS Security/IDgroups (all)

- CSSS Group leaders (to spot train volunteers)

Equipment:

- 1 intake tables

- 4 chairs

- equipment to create and place identification on adult volunteers (bracelet or other, color coded, bar coded, badges, t-shirts?, colored vests?)

- equipment to read, check, transmit data for background checks

- equipment to create hard copy and/or electronically store lists and tracking of adult volunteers

- “INTAKE” forms for adult volunteers

- Paper, scissors, tape, pens

- Civilian technology:.. cell phones, pdas, laptops, digital cameras (still and/or video) (would OnStar equipped vehicle be available?)

Scenario:

In the hours immediately after the earthquake a small group of adult civilians self-organized to create a safe area for children in the Rose Bowl parking lot.  Several people have volunteered to help with the kids, but the civilian leadership team  (including teachers and day care providers) recognizes the desirability of having background checks on people with proximity/access to children.

Civilian volunteers, including parents and school chaperones, have recognized the need to secure children in a safe location and have cordoned off an area and are seeking means to engage with first responders to address the needs of children.

Purpose of the Activity:

The purpose of the activity is two-fold.  First, to provide for the safety and security of children by screening all adult volunteers who will work in proximity to them.  Second, to determine how civilian volunteers and/or responding agencies can qualify spontaneous adult volunteers at a disaster scene to work directly with or in close proximity to children.   Qualification includes assessing the capabilities, background checking, and conducting spot-training for adult volunteers prior to assigning them to roles.

Key Objectives:

- Process through intake and tag a minimum of 10 adult volunteers

- Conduct on-site background checks on a minimum of 10 adults

- Ensure that every adult with children during the day has received clearance from the CSSS security/id group.

Process Flow:

Volunteer Intake:  Adult volunteers will arrive at the OFR-HoldSafe intake area directly after clearing OGP security.  Simultaneous to the identification of children, arriving adult volunteers will also be identified, interviewed, screened (background check) and, if cleared, assigned to a volunteer job on site.  [Excess volunteers may be available for other OFR activities.]  Uncleared adults will move to observer location, will be directed to other OFR roles, or will leave the stie.

Volunteer Assignment/Training:  Volunteers will move to their job locations, where they will receive a short briefing/training and then will flow into the activities of the CSSS.

Critical Considerations

Liability Waiver:  For each adult there will not only be an individual badge/tag created, but also a folder with any release form that must be signed in order to proceed with intake at the CSSS site.

No adult should enter the CSSS inner perimeter without appropriate identification and clearance through OFR-HoldSafe Intake.

We will aim to qualify as many civilian volunteers as needed to conduct site operations effectively, within the parameter of ensuring that all adults in contact with or with access to children will present no threat to children.

TTX Issues to resolve:

- How do we ID/tag children and adult simultaneously?

- Are there low-tech, workable civilian means of tagging in immediate hours after a disaster?

- Are tags for kids the same type as those for screened adult volunteers?

- What sort of non-transferable, non-duplicable identification might be used for screened adults?

- What are the rules of play for parents/guardians who are not volunteering?  Can they accompany their child?  Must a volunteer escort?

- How will we divide up tests for different/competing ID/tagging solutions?

- Do we need power sources for making and storing information on ID/tags

- How can we conserve power sources and have data readily available over several days?

- What comms that are on site need to play in this process?  How does this fit with the exercise objective to utilize civilian comms to the greatest extent possible?

EXERCISE ACTIVITY 4:

KIDS’ MEDICAL TRIAGE, TREATMENT

Time: 		TBD

Place: 	OFR-HoldSafe CSSS Factility

Players:

- Tagged medical needs kids with guardian or assigned volunteer shepherd

- Pediatric nurse

- Attorney

- Premier/ hospital reps

- Kids tagging reps

- Motorola/ Verizon comms reps

- Command observers

Equipment:

- Cell phones designated in comms exercise for use in securing urgent medical care

- Lap tops designated in comms exercise for use in urgent medical care

- Photo equipment designated for urgent medical care

- First aid supplies and equipment found on site or provided by volunteers

- Ham operator and equipment if available

- Civilian created medical records from Hold Safe nurse and /or tag recorder/reader

- Call/web contact information on civilian medical/hospital

- Symptomology cards

- Electronic equipment containing medical data storage

- NCMEC

Scenario:

In the first phase of the exercise, representing the first 24 hours post event, children with urgent medical needs will be given care by emergency responders and/or the civilian CSSS medical team, including a pediatric nurse.  Communications volunteers will need to  work with hospital reps to get appropriate area hospital staff on calls and to provide direction on next steps for the nurse, including what requests for treatment supplies and/or transportation need to be sent out by communications players. Communications players will need to also determine what medical data needs to be sent out and where. Legal issues on the treatment of children without adult family members’ consent will need to be resolved.

If a ham radio operator and equipment are on site, the ham operator should shadow the exercise and make notes as to how this technology could be useful.  If time and integration allows, then the ham interfaces should be tested.

A medical history has been created that is limited by on-site circumstances and the degree to which help has been obtained by outside medical facilities/personnel.  If possible, calls have been placed for first responder treatment-specific medicines and supplies for the kids in medical stress.

Purpose of the Exercise:

These activities are designed to determine what civilians can do in the hours immediately after a disaster to address the immediate medical needs of kids on-site and then get outside medical instruction and guidance, using available civilian owned technology.  The activities will test the ability of civilian volunteers to connect with local hospital specialists, and transmit critical medical data. It will also test the ability of these volunteers  to get medical supply needs/orders out to first responders, and determine who those responders should/need to be—before first responders appear on  site.

Key Objectives:

- Screen all arriving children for medical needs.

- Provide for continuity of care by developing case notes/treatment information by civilian team

- Utilize civilian communications to alert first responders of pediatric medical needs and if possible connect to local hospitals as resources.

- If/when hand-off of child to medical teams takes place, ensure ongoing tracking of child’s whereabouts and critical identification data.

Process Flow:

As children are processed through intake at the CSSS they will be screened by the OFR-HoldSafe medical group and pediatric nurse for further analysis and first aid.  Nurse will triage case needs (symptomology/profile cards).  Decisions will need to be made to determine if volunteers need to remain with medical needs children.  Treatment will be provided where needed.  The CSSS medical group will work with the OFR-HoldSafe communications group to try to establish communication with first responders to request medical assistance and information.

Critical Considerations:

Civilian volunteers will need to assure that they “do no further  harm”  providing urgent care on site.

TTX Issues to resolve:

- Beyond initial screening what role will the nurse play?

- Do these kids need additional tagging; what kind?

- What medical information needs to be sent to the NCMEC? How can this exercise be streamlined, and yet insure that issues, communications devices and policy issues are fully vetted?

- How will Premier interface with its hospitals versus direct connections to hospitals.

- Do NCMEC  and federal government now co-share the Congressionally mandated NCMEC locator responsibility?

- Are there any other legal issues that pertain to state, local, or NGO authority?

EXERCISE ACTIVITY 5:

KIDS’ MEDICAL CIVILIAN/MILITARY INTEGRATION

Time: 		TBD

Place(s): 	OFR-HoldSafe CSSS Factility; OGP/OFR Telemed facility at Rose Bowl location; OGP Navy medical facility at Rose Bowl location.

Players:

- Doctors and technicians of OGP/OFR med and telemed unit

- Tagged medical needs kids with guardian or assigned volunteer shepherd

- Pediatric nurse

- Attorney

- Premier/ hospital reps

- Kids tagging reps

- Motorola/ Verizon comms reps

- Command observers

- preliminary advisors

Equipment:

- Cell phones designated in comms exercise for use in securing urgent medical care

- Lap tops designated in comms exercise for use in urgent medical care

- Photo equipment designated for urgent medical care

- First aid supplies and equipment found on site or provided by volunteers

- Ham operator and equipment if available

- Exercise established OGP/OFR tele-medical unit

- Exercise established Navy medical unit

- Pre ordered civilian drug needs in kids doses

- Civilian created medical records from Hold Safe nurse and /or tag recorder/reader

- Call/web contact information on civilian medical/hospital

- Symptomology cards

- Electronic equipment containing medical data storage

- NCMEC

Scenario:

In the first phase of the medical exercise, the civilian CSSS medical team, sought to address medical issues of children.  This second phase of the exercise will be time accelerated to the second day post-event, when military medical units will have arrived  The civilian/ military integration will seek to secure on-site treatment for kids with medical needs utilizing both military tele-med capabilities and on-site OGP Navy medical personnel.

Purpose of the Exercise:

The activities are designed to explore how civilian-centric volunteer responses merge into an orderly hand-off to federal government first responders; in this case military medical units.  It is important to build on the information and treatment that civilian volunteers have garnered and have been able to send out to appropriate disaster responders/facilitators.  Tagging and tracking systems are useful and effective only if they are maintained and updated. Initial efforts by civilians should be as simple as possible, but meet the basic needs of the NCMEC for tracking and transferring children. Initiation of such systems by civilian volunteers should actually “jump-start” family reunification while holding kids safe until first responders arrive.

Key Objectives:

- Transmit data on critical medical needs of at least 5 children to responding military medical personnel and/or tele-medical resources.

- Provide medical care for at least 2 children by gaining access to the medical facility established on site during the field exercise.

- Provide continuity of care by providing case notes/treatment information from civilian team to military medical teams

- Ensure tracking of children will continue if/when hand off of child is made to military teams.

Process Flow:

In this second day post-disaster,  symptomology cards will call for medical conditions of some children to present urgent needs for treatment, including asthma, diabetes, etc.  The OFR-HoldSafe team will seek to access available OGP/OFR tele-medical resources for 2-3 cases.  This will require liaison with military units and eventual relocation of children to OGP locations on the exercise site.

Critical Considerations:

Civilian volunteers will need to assure that they “do no further  harm”  providing urgent care on site.  Additionally, movement of children from the inner OFR-HoldSafe perimeter to OGP/OFR medical facilities will require appropriate check-out, shepherding, and tracking procedures, as well as creation of accurate treatment histories for each child with medical needs.  All pertinent information and medical tags/symptomologies on each child’s case, initial treatment plan, and sources of medical advice should be included.  If kids need to be relocated, legal status/issues of transport should be already resolved or played out.  Capability of NCMEC continued tracking of kids that are handed off into military custody should be addressed.

TTX Issues to resolve:

- Beyond initial screening/treatment what role will the nurse play?

- How will Premier interface with its hospitals versus direct connections to hospitals.

- How do we maintain this as a relatively pure civilian exercise that simply self organizes verses a later exercise that is more medically detailed, and provides help through GP med units and telemed conferencing.

- Are there military rules of engagement/ accepting civilians into med units and transport that need to be taken into consideration?

- Is the transfer of power to the US government assumed or formalized?

- Do NCMEC  and federal government now co-share the Congressionally mandated NCMEC locator responsibility?

- Are there any other legal issues that pertain to state, local, or NGO authority?

- Will kid tags and medical symtomologies merge/interface with military tracking/documentation?

- Are there any interfaces/ tracking issues for NCMEC that need to be addressed with governmental agencies and we can test with the military med unit?

- What are the timeline needs/concerns and processing issues that need to be addressed in transitioning each child and guardian from OFR/Hold Safe to GP med unit ?

- If kids are transferred by military to another federal military unit/transport, state or local unit, how is the tracking of kids continued and fed into NCMEC?

- Are there hand-off protocols that should be devised?

EXERCISE ACTIVITY 6

KIDS’ EMERGENCY LEGAL REVIEW AND ADJUDICATION

Mike Berry to prepare

Time: 		TBD

Place(s): 	OFR-HoldSafe CSSS Factility; OGP/OFR Telemed facility at Rose Bowl location;

Players:

- Tagged legal needs kids with guardian or assigned volunteer shepherd

- Attorney

- Kids tagging reps

- OFR-HoldSafe Comms Group and advisors

- NCMEC personnel

- Command observers

Equipment:

- OFR-HoldSafe Comms Equipment

- Ham operator and equipment if available

- Exercise established OGP/OFR tele-medical unit

- Civilian created legal documents from CSSS Emergency Legal group

- Call/web contact information on regional administrative courts/judges

- Symptomology/profile cards

Scenario:

Purpose of the Exercise:

Process Flow:

Critical Considerations:

TTX Issues to resolve:

EXERCISE ACTIVITY 6

CHILD SAFETY, SECURITY, AND SHELTER (CSSS) DEMONSTRATION

Lenore, Paige and Mike to prepare

Time: 		TBD

Place(s): 	OFR-HoldSafe CSSS Facility

Players:

- All minor children/clients on site

- All OFR-HoldSafe operations and support teams

- Command observers and evaluators

Equipment:

- OFR-HoldSafe CSSS equipment per footprint diagram

- Additional CSSS supplies

- Lunch for OFR-HoldSafe team members and volunteers

- Project K.I.D. PlayCare supplies

- Symptomology/profile cards

Scenario:

Purpose of the Exercise:

Process Flow:

Critical Considerations:

TTX Issues to resolve:

# Appendix F – EXERCISE RESOURCE SUMMARY

# Footnotes

The Highlands Forum is an informal, cross-disciplinary network, chaired by the Assistant Secretary of Defense (Networks and Information Integration), with an interest in information, science, and technology and their impact on global and societal activities. Industry, academia, government, and professionals from a variety of fields share their knowledge and insights about the development and effects of technologies in the information realm. Some of the areas explored by the Forum are emerging technologies, organizational development, economic competition, and the changing concept of security. The Forum serves as a catalyst for creativity and enhanced decision-making by policy makers.

Project K.I.D., Inc. is a 501(c)(3) public charity that exists to promote intentional and coordinated emergency preparedness and response activities that address the specific needs of children in times of disaster and devastation.  Based on our experiences in Mississippi, Alabama, and Louisiana following Hurricane Katrina, Project K.I.D. seeks to facilitate the development of local, regional, and nation-wide systems of preparation and response that can provide 1) immediate physical safety and security for children, 2) attention to their emergency and ongoing medical needs, 3) response and recovery environments that promote the psychosocial resilience of children, and 4) respite for families in distress taking care of children during the early phases of disaster recovery.  Project K.I.D. has prepared a white paper, To Hold Safe:  Framing a New Era of Disaster Child Care, that provides an overview of the state of disaster preparation around the needs of children at the time of Hurricane Katrina.  This white paper is available upon request or online at www.project-kid.org.   OFR-HoldSafe is being undertaken to help us refine our recommendations for ongoing preparedness activities among civilian, civil, and military groups to address the needs of kids in disasters.

In the event of a natural disaster, the National Emergency Child Locator Center will:

- Establish a toll-free hotline to receive reports of displaced children;

- Create a website to provide information about displaced children;

- Deploy staff to the location of a declared disaster area to gather information about displaced children;

- Provide information to the public about additional resources;

- Partner with federal, state, and local law enforcement agencies; and

- Refer reports of displaced adults to the Attorney General’s designated authority and the National Emergency Family Registry and Locator System.

# Text boxes

Shelter/Legal Task Force

Director: MCB assigned

Volunteers

Supported by OFR telecomm resources for “telejudge” event

Disaster Child Care/Shepherding  Task Force

Director: Lydia Guerzon

Volunteers

Jacob Baldwin

Pediatric Medical Task Force

Director: Norma Hamilton

Volunteers

Supported by Premier &

OFR Tele-med personnel

Security/ID Task Force

Director:

Volunteer TBD

NCMEC Personnel

Supported by

Comms Resources

OPERATIONS SECTION

Section Chief:

Michael Berry

Deputy:

Paige Ellison-Smith