## FV Projects
ID | Description | Latitude | Longitude | Elevation | Elevation_Source | Pt_Quality | Area | Country_Code | Dtd_ID | Horz_Accuracy | Vert_Accuracy | Link_Name | Icon_Name | Comment | Group_Name
1 | Alingar CHC + EOC | 34.8328 | 70.3647 | [9 empty] | purp dot2 | Alingar CHC + EOC | USAID
2 | Qalatak Girls Primary School | 34.7508 | 70.3081 | [9 empty] | purp dot2 | Qalatak Girls Primary School | USAID
3 | New Badi Abad School | 34.7353 | 70.2825 | [9 empty] | gren_dot | New Badi Abad School | USAID
4 | New Alingar Basic Clinic | 34.7514 | 70.3164 | [9 empty] | gren_dot | New Alingar Basic Clinic | USAID
5 | Rehab Sangar School | 34.8361 | 70.3597 | [9 empty] | purp dot2 | Rehab Sangar School | USAID
6 | Rehab Shikh Mohammad Hussain School | 34.7989 | 70.3261 | [9 empty] | purp dot2 | Rehab Shikh Mohammad Hussain School | USAID
7 | Rehab Shahid Abdul Wahib School | 34.58 | 70.5961 | [9 empty] | purp dot2 | Rehab Shahid Abdul Wahib School | USAID
8 | Construction of Alingar District Gov't Bldg | 34.8325 | 70.3644 | [9 empty] | gren_dot | Construction of Alingar District Gov't Bldg | USAID
9 | New Barigza'i School | 34.7122 | 70.1392 | [9 empty] | gren_dot | New Barigza'i School | USAID
10 | Rehab Ali Shang High School | 34.5867 | 70.5992 | [9 empty] | purp dot2 | Rehab Ali Shang High School | USAID
11 | Gamba CHC | 34.7833 | 70.1078 | [9 empty] | purp dot2 | Gamba CHC | USAID
12 | Shaheed Tariq Middle School | 34.7503 | 70.1156 | [9 empty] | purp dot2 | Shaheed Tariq Middle School | USAID
13 | Islamabad Girls Middle School | 34.7536 | 70.0992 | [9 empty] | purp dot2 | Islamabad Girls Middle School | USAID
14 | Ganjawon Girls Primary School | 34.7106 | 70.1394 | [9 empty] | purp dot2 | Ganjawon Girls Primary School | USAID
15 | New Badpas Comprehensive Clinic | 34.6442 | 69.9086 | [9 empty] | gren_dot | New Badpas Comprehensive Clinic | USAID
16 | # 2 Tajribawi Middle School | 34.66 | 70.2056 | [9 empty] | purp dot2 | # 2 Tajribawi Middle School | USAID
17 | Roshan High School Block B | 34.6617 | 70.2097 | [9 empty] | purp dot2 | Roshan High School Block B | USAID
18 | Roshan High School Block A | 34.6617 | 70.2097 | [9 empty] | purp dot2 | Roshan High School Block A | USAID
19 | Harmole High School | 34.6956 | 70.2292 | [9 empty] | purp dot2 | Harmole High School | USAID
20 | Qala-e-Naw Middle School | 34.7103 | 70.2419 | [9 empty] | purp dot2 | Qala-e-Naw Middle School | USAID
21 | # 1 Middle School Block A | 34.6739 | 70.2114 | [9 empty] | purp dot2 | # 1 Middle School Block A | USAID
22 | # 1 Middle School Block B | 34.6739 | 70.2114 | [9 empty] | purp dot2 | # 1 Middle School Block B | USAID
23 | Ali Khil Middle School | 34.6786 | 70.2 | [9 empty] | purp dot2 | Ali Khil Middle School | USAID
24 | Mehtarlamak High School | 34.6472 | 70.195 | [9 empty] | purp dot2 | Mehtarlamak High School | USAID
25 | Mashakhel Middle School | 34.5808 | 70.2081 | [9 empty] | purp dot2 | Mashakhel Middle School | USAID
26 | Shamangal Primary School | 34.6425 | 70.2239 | [9 empty] | purp dot2 | Shamangal Primary School | USAID
27 | Mehtarlamak Girls Primary School | 34.6475 | 70.1944 | [9 empty] | purp dot2 | Mehtarlamak Girls Primary School | USAID
28 | Kutubzai Girls Primary School | 34.6864 | 70.1772 | [9 empty] | purp dot2 | Kutubzai Girls Primary School | USAID
29 | Qarghai CHC | 34.5469 | 70.2431 | [9 empty] | purp dot2 | Qarghai CHC | USAID
30 | Kakus clinic | 34.5064 | 70.0361 | [9 empty] | purp dot2 | Kakus clinic | USAID
31 | Gul Pach Ulfat High School | 34.4936 | 70.2986 | [9 empty] | purp dot2 | Gul Pach Ulfat High School | USAID
32 | Surkhakan High School | 34.5078 | 70.2111 | [9 empty] | purp dot2 | Surkhakan High School | USAID
33 | Naht-e-Karim Priamary School | 34.5306 | 70.3272 | [9 empty] | purp dot2 | Naht-e-Karim Priamary School | USAID
34 | Kaku Middle School | 34.5069 | 70.0344 | [9 empty] | purp dot2 | Kaku Middle School | USAID
35 | Holding Bin | 34.2744 | 70.7361 | [9 empty] | purp dot2 | Holding Bin | USAID
36 | Market Collection Ctr | 34.2692 | 70.7414 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
37 | Farm Ghaziabad Primary School | 34.2764 | 70.7689 | [9 empty] | purp dot2 | Farm Ghaziabad Primary School | USAID
38 | Rehab Pashtunistan School | 34.0081 | 70.0472 | [9 empty] | purp dot2 | Rehab Pashtunistan School | USAID
39 | Holding Bin | 34.4525 | 70.465 | [9 empty] | purp dot2 | Holding Bin | USAID
40 | Behsud CHC | 34.4514 | 70.5156 | [9 empty] | purp dot2 | Behsud CHC | USAID
41 | Saracha-e-Ali Khan Primary School | 34.3683 | 70.5333 | [9 empty] | purp dot2 | Saracha-e-Ali Khan Primary School | USAID
42 | Kareez Kabir Primary School | 34.3697 | 70.5194 | [9 empty] | purp dot2 | Kareez Kabir Primary School | USAID
43 | Tralay Chaparhar BHC | 34.3306 | 70.4278 | [9 empty] | purp dot2 | Tralay Chaparhar BHC | USAID
44 | Clinic | 34.2361 | 70.3294 | [9 empty] | purp dot2 | Clinic | USAID
45 | Market Collection Ctr | 34.7067 | 70.5683 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
46 | Market Collection Ctr | 43.7128 | 70.5683 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
47 | Dehbala CHC | 34.1178 | 70.4617 | [9 empty] | purp dot2 | Dehbala CHC | USAID
48 | Market Collection Ctr | 34.0553 | 70.9261 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
49 | Market Collection Ctr | 34.4342 | 70.4381 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
50 | Goshta CHC | 34.3544 | 70.795 | [9 empty] | purp dot2 | Goshta CHC | USAID
51 | Goshta Intake and Cleaing (cluster village 1) | 34.3786 | 70.7219 | [9 empty] | purp dot2 | Goshta Intake and Cleaing (cluster village 1) | USAID
52 | Goshta Intake and Cleaing (cluster village 1), Miagano Canal Cleaning | 34.3628 | 70.7933 | [9 empty] | purp dot2 | Goshta Intake and Cleaing (cluster village 1), Miagano Canal Cleaning | USAID
53 | Goshta Intake and Cleaing (cluster village 1), Khowezi Intake and Cleaning | 34.3594 | 70.7711 | [9 empty] | purp dot2 | Goshta Intake and Cleaing (cluster village 1), Khowezi Intake and Cleaning | USAID
54 | Goshta Intake and Cleaing (cluster village 1), Khowezi Intake and Cleaning | 34.3692 | 70.725 | [9 empty] | purp dot2 | Goshta Intake and Cleaing (cluster village 1), Khowezi Intake and Cleaning | USAID
55 | Khowezi Intake and Cleaning (cluster village 2), Khowezi village intake and canal cleaning | 34.3583 | 70.765 | [9 empty] | purp dot2 | Khowezi Intake and Cleaning (cluster village 2), Khowezi village intake and canal cleaning | USAID
56 | Rehab Jokan School | 34.3067 | 69.7194 | [9 empty] | purp dot2 | Rehab Jokan School | USAID
57 | Rehab Koz Sayab School | 34.2572 | 70.0022 | [9 empty] | purp dot2 | Rehab Koz Sayab School | USAID
58 | Market Collection Ctr | 34.2772 | 69.8522 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
59 | Market Collection Ctr | 34.2722 | 69.775 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
60 | Durunta Dam | 34.4839 | 70.3608 | [9 empty] | gren_dot | Durunta Dam | USAID
61 | Kan Qatraghi BHC | 34.2656 | 70.4875 | [9 empty] | purp dot2 | Kan Qatraghi BHC | USAID
62 | Joye Haft (S) | 34.4236 | 70.4319 | [9 empty] | purp dot2 | Joye Haft (S) | USAID
63 | Naswan # 2 High School | 34.4383 | 70.4325 | [9 empty] | purp dot2 | Naswan # 2 High School | USAID
64 | Bibi Aisha Sadiq (S) | 34.4281 | 70.4711 | [9 empty] | purp dot2 | Bibi Aisha Sadiq (S) | USAID
65 | Workshop in 23 Districts of Nangarhar | 34.7244 | 70.7658 | [9 empty] | purp dot2 | Workshop in 23 Districts of Nangarhar | USAID
66 | Market Collection Ctr | 34.3706 | 70.7764 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
67 | Market Collection Ctr | 34.4194 | 70.5878 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
68 | Market Collection Ctr | 34.4119 | 70.6403 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
69 | Holding Bin | 34.4047 | 70.5856 | [9 empty] | purp dot2 | Holding Bin | USAID
70 | Sangar Saray/Kama CHC | 34.4106 | 70.6389 | [9 empty] | purp dot2 | Sangar Saray/Kama CHC | USAID
71 | Sangar Saray (S) | 34.4128 | 70.6414 | [9 empty] | purp dot2 | Sangar Saray (S) | USAID
72 | Akhund High School for Boys | 34.4169 | 70.5747 | [9 empty] | purp dot2 | Akhund High School for Boys | USAID
73 | Holding Bin | 34.2369 | 70.1828 | [9 empty] | purp dot2 | Holding Bin | USAID
74 | Ahmad Khel Wazir CHC | 34.2108 | 70.1753 | [9 empty] | purp dot2 | Ahmad Khel Wazir CHC | USAID
75 | Wazir Farakhel CHC | 34.2 | 70.1814 | [9 empty] | purp dot2 | Wazir Farakhel CHC | USAID
76 | Said Ahmad Khan | 34.1453 | 70.6 | [9 empty] | purp dot2 | Said Ahmad Khan | USAID
77 | Market Collection Ctr | 34.5381 | 70.5467 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
78 | Market Collection Ctr | 34.5567 | 70.6194 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
79 | Market Collection Ctr | 34.8214 | 70.9803 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
80 | Market Collection Ctr | 34.915 | 70.9861 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
81 | Holding Bin | 34.5886 | 70.5806 | [9 empty] | purp dot2 | Holding Bin | USAID
82 | Gurag Khewa BHC | 34.5564 | 70.21 | [9 empty] | purp dot2 | Gurag Khewa BHC | USAID
83 | Syed Jamaluddin Afghani High School | 34.5561 | 70.5686 | [9 empty] | purp dot2 | Syed Jamaluddin Afghani High School | USAID
84 | Kuzkunar Badyali Kali Water Reservoir (cluster village 1) | 34.6078 | 70.6233 | [9 empty] | purp dot2 | Kuzkunar Badyali Kali Water Reservoir (cluster village 1) | USAID
85 | Kuzkunar Badyali Kali Water Reservoir (cluster village 2) | 34.6078 | 70.6233 | [9 empty] | purp dot2 | Kuzkunar Badyali Kali Water Reservoir (cluster village 2) | USAID
86 | Kuzkunar Badyali Kali Water Reservoir (cluster village3) | 35.0097 | 71.0347 | [9 empty] | purp dot2 | Kuzkunar Badyali Kali Water Reservoir (cluster village3) | USAID
87 | Kuzkunar Badyali Kali Water Reservoir (cluster village 4) | 34.6197 | 70.5547 | [9 empty] | purp dot2 | Kuzkunar Badyali Kali Water Reservoir (cluster village 4) | USAID
88 | Market Collection Ctr | 34.2417 | 71.0469 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
89 | Market Collection Ctr | 34.2636 | 70.8983 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
90 | Lalpur Chaknoor Retaining Wall, Canal Cleaning and Wash Culverts (cluster village 1) | 34.2678 | 70.9069 | [9 empty] | purp dot2 | Lalpur Chaknoor Retaining Wall, Canal Cleaning and Wash Culverts (cluster village 1) | USAID
91 | Lalpur Chaknoor Retaining Wall, Canal Cleaning and Wash Culverts (cluster village 2) | 34.2672 | 70.9308 | [9 empty] | purp dot2 | Lalpur Chaknoor Retaining Wall, Canal Cleaning and Wash Culverts (cluster village 2) | USAID
92 | Lalpur Chaknoor Retaining Wall, Canal Cleaning and Wash Culverts (cluster village 3) | 34.2622 | 70.9728 | [9 empty] | purp dot2 | Lalpur Chaknoor Retaining Wall, Canal Cleaning and Wash Culverts (cluster village 3) | USAID
93 | Chaknawar village cluster 1 retaining wall, Canal Cleaning and Wash Culverts | 34.2625 | 70.9625 | [9 empty] | purp dot2 | Chaknawar village cluster 1 retaining wall, Canal Cleaning and Wash Culverts | USAID
94 | Lalpur and Sada Instake and Canal Cleaning (cluster village 1) | 34.2581 | 70.9961 | [9 empty] | purp dot2 | Lalpur and Sada Instake and Canal Cleaning (cluster village 1) | USAID
95 | New Mohmand Darah District Judicial Facility | 34.2439 | 70.8806 | [9 empty] | purp dot2 | New Mohmand Darah District Judicial Facility | USAID
96 | Market Collection Ctr | 34.2167 | 71.0389 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
97 | Market Collection Ctr | 34.2342 | 70.9603 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
98 | Market Collection Ctr | 43.4097 | 71.4825 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
99 | Aimal Khan High School | 34.2433 | 70.8822 | [9 empty] | purp dot2 | Aimal Khan High School | USAID
100 | Daka Primary School | 34.2136 | 71.055 | [9 empty] | purp dot2 | Daka Primary School | USAID
101 | Market Collection Ctr | 34.0861 | 70.8025 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
102 | Market Collection Ctr | 34.0614 | 70.8181 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
103 | Market Collection Ctr | 34.1267 | 70.2906 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
104 | New Rodat Basic Clinic | 34.2581 | 70.6444 | [9 empty] | gren_dot | New Rodat Basic Clinic | USAID
105 | Rehab Kan School | 34.2694 | 70.51 | [9 empty] | purp dot2 | Rehab Kan School | USAID
106 | Hisarshahi Camp Primary School | 34.3133 | 70.6228 | [9 empty] | purp dot2 | Hisarshahi Camp Primary School | USAID
107 | Rodat Musftee Retaining Wall (Muftee cluster village 1) | 34.2539 | 70.5744 | [9 empty] | purp dot2 | Rodat Musftee Retaining Wall (Muftee cluster village 1) | USAID
108 | Rodat Musftee Retaining Wall (cluster village 2) | 34.2583 | 70.5939 | [9 empty] | purp dot2 | Rodat Musftee Retaining Wall (cluster village 2) | USAID
109 | Rodat Muftee Retaining wall (cluster village 3), Qazi Qala | 34.2519 | 70.575 | [9 empty] | purp dot2 | Rodat Muftee Retaining wall (cluster village 3), Qazi Qala | USAID
110 | Rodat Flood Protection Kom - Baro | 34.4386 | 71.0769 | [9 empty] | purp dot2 | Rodat Flood Protection Kom - Baro | USAID
111 | New Shirzad Primary School | 34.2478 | 69.9958 | [9 empty] | gren_dot | New Shirzad Primary School | USAID
112 | Rehab Shirzad High School | 34.2558 | 70.0056 | [9 empty] | purp dot2 | Rehab Shirzad High School | USAID
113 | Sherzad Manakhel CHC | 34.2503 | 69.9981 | [9 empty] | purp dot2 | Sherzad Manakhel CHC | USAID
114 | Sherzad Marki Khil BHC | 34.2081 | 70.0286 | [9 empty] | purp dot2 | Sherzad Marki Khil BHC | USAID
115 | Road from Marko Village to Ghanikhel Village | 67.0525 | 38.5303 | [9 empty] | gren_dot | Road from Marko Village to Ghanikhel Village | USAID
116 | New Gheni Khil District Judicial Facility | 34.2008 | 70.7967 | [9 empty] | purp dot2 | New Gheni Khil District Judicial Facility | USAID
117 | Market Collection Ctr | 34.4397 | 70.4433 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
118 | Market Collection Ctr | 34.2594 | 70.8114 | [9 empty] | purp dot2 | Market Collection Ctr | USAID
119 | Holding Bin | 34.4492 | 70.3694 | [9 empty] | purp dot2 | Holding Bin | USAID
120 | Balabagh CHC | 34.395 | 70.2217 | [9 empty] | purp dot2 | Balabagh CHC | USAID
121 | Baghbani BHC | 34.3856 | 70.21 | [9 empty] | purp dot2 | Baghbani BHC | USAID
122 | Amarkhel BHC | 34.4628 | 70.35 | [9 empty] | purp dot2 | Amarkhel BHC | USAID
123 | Qala-e-Maroof Primary School | 34.4342 | 70.3678 | [9 empty] | purp dot2 | Qala-e-Maroof Primary School | USAID

## Proj MGRS Coords
Police Facility | 0 | 0 | XD 3154 1189 | Police Facility | USAID |  |  | ?
Clinic protection wall/ gate/ latrines | 0 | 0 | 42S WD 975 695 | Clinic protection wall/ gate/ latrines | CERP | Laghman | wait for clinic completion | 0%
District Koyghani | 0 | 0 | 42S XC 097 910 | District Koyghani | CERP | Nangarhar | Pending Approval | 0%
Khogyani Primary School (Sorma) | 0 | 0 | 42S XC 109923 | Khogyani Primary School (Sorma) | CERP | Nangarhar | QA/QC | 100%
Girl's School Protection Wall/ Gate | 0 | 0 | 42S XC 109923 | Girl's School Protection Wall/ Gate | CERP | Nangarhar | Bidders Conf | 0%
Sangani Primary School | 0 | 0 | 42S XC 109923 | Sangani Primary School | OHDACA | Nangarhar | BIDDERS CONF 27 Apr 05 | 0%
Kambu School | 0 | 0 | 42S XC 1120 8380 | Kambu School | CERP | Nangarhar | QA/QC | 90%
University Addition | 0 | 0 | 42S XC 1200 8324 | University Addition | CERP | Nangarhar | Complete | 100%
Repair ACM Vandelism (Merkhani School) | 0 | 0 | 42S XC 141 720 | Repair ACM Vandelism (Merkhani School) | CERP | Nangarhar | Complete | 100%
Merkani Clinic | 0 | 0 | 42S XC 145 728 | Merkani Clinic | CERP | Nangarhar |  | 40%
Merkhani Elementary School (Tora Bora) | 0 | 0 | 42S XC 145 728, 42S XC 144 720 | Merkhani Elementary School (Tora Bora) | OHDACA | Nangarhar | Complete | 100%
Carpets for Gari Khel School | 0 | 0 | 42S XC 1450 7720 | Carpets for Gari Khel School | CERP | Nangarhar | Complete | 100%
Landakhil Health Clinic | 0 | 0 | 42S XC 173 860 | Landakhil Health Clinic | OHDACA | Nangarhar | Pending Approval | 0%
Landakhil Primary School | 0 | 0 | 42S XC 17988617 | Landakhil Primary School | CERP | Nangarhar | QA/QC | 85%
District Pachir Wa Agam | 0 | 0 | 42S XC 183 852 | District Pachir Wa Agam | CERP | Nangarhar | Pending Approval | 0%
Koseagam Primary School | 0 | 0 | 42S XC 19278898 | Koseagam Primary School | CERP | Nangarhar | QA/QC | 80%
Ghirikihl Primary School | 0 | 0 | 42S XC 192889 | Ghirikihl Primary School | CERP | Nangarhar | QA/QC | 90%
Lockhay Community School | 0 | 0 | 42S XC 245 980 | Lockhay Community School | CERP | Nangarhar | Complete | 100%
Ambulance | 0 | 0 | 42S XC 2525 9362 | Ambulance | CERP | Nangarhar | Complete | 100%
Water pump/school | 0 | 0 | 42S XC 2535 9362 | Water pump/school | CERP | Nangarhar | Complete | 100%
Sports field | 0 | 0 | 42S XC 2535 9362 | Sports field | CERP | Nangarhar | Complete | 0%
Generator/health clinic | 0 | 0 | 42S XC 2540 9361 | Generator/health clinic | CERP | Nangarhar | Complete | 100%
Orphanage Refurbishment | 0 | 0 | 42S XC 6563 8562 | Orphanage Refurbishment | CERP | Nangarhar | Complete | 100%
Clinic Generator Pckg | 0 | 0 | 42S XC 6563 8562 | Clinic Generator Pckg | CERP | Nangarhar | Complete | 100%
Ambulance | 0 | 0 | 42S XC 6563 8562 | Ambulance | CERP | Nangarhar | locate vehicle | 0%
Shinwaro Loya Elementary School - repair | 0 | 0 | 42S XC 65645 85597 | Shinwaro Loya Elementary School - repair | OHDACA | Nangarhar | Complete | 100%
Refurbish High School in Alishang | 0 | 0 | 42S XD 012 498 | Refurbish High School in Alishang | CERP | Laghman | Complete | 98%
Girls School in Alishang | 0 | 0 | 42S XD 012 498 | Girls School in Alishang | CERP | Laghman | Complete | 90%
Boys School in Alishang | 0 | 0 | 42S XD 012 498 | Boys School in Alishang | CERP | Laghman | QA/QC | 75%
School Water system | 0 | 0 | 42S XD 012 498 | School Water system | CERP | Laghman | QA/QC | 15%
Micro-Hydro | 0 | 0 | 42S XD 019 489 | Micro-Hydro | CERP | Laghman | Pending Approval | 0%
Generator/health clinic | 0 | 0 | 42S XD 058 407 | Generator/health clinic | CERP | Laghman | Complete | 100%
Ambulance | 0 | 0 | 42S XD 058 407 | Ambulance | CERP | Laghman | Complete | 100%
Lights/Fans for Clinic | 0 | 0 | 42S XD 058 407 | Lights/Fans for Clinic | CERP | Laghman | Complete | 100%
Tool Packages | 0 | 0 | 42S XD 058 407 | Tool Packages | CERP | Laghman | Complete | 100%
Hand pump for School well | 0 | 0 | 42S XD 0781 3784 | Hand pump for School well | CERP | Laghman | Complete | 100%
Water system for school | 0 | 0 | 42S XD 0781 3874 | Water system for school | CERP | Laghman | Complete | 100%
Tables/desks for ANA | 0 | 0 | 42S XD 080 350 | Tables/desks for ANA | CERP | Laghman | Complete | 100%
Water truck | 0 | 0 | 42S XD 080 350 | Water truck | CERP | Laghman | Complete | 100%
Tool Package for PW Dept. | 0 | 0 | 42S XD 080 350 | Tool Package for PW Dept. | CERP | Laghman | Complete | 100%
Garbage truck | 0 | 0 | 42S XD 080 350 | Garbage truck | CERP | Laghman | Complete | 100%
Provincial Office Repair | 0 | 0 | 42S XD 091 350 | Provincial Office Repair | CERP | Laghman | QA/QC | 95%
Provincial Police HQ Generators | 0 | 0 | 42S XD 091 350 | Provincial Police HQ Generators | CERP | Laghman | Complete | 0%
Provincial Jail Generators/ Fans | 0 | 0 | 42S XD 091 350 | Provincial Jail Generators/ Fans | CERP | Laghman | Complete | 0%
Flying coach van (women's affair) | 0 | 0 | 42S XD 098354 | Flying coach van (women's affair) | CERP | Laghman | Complete | 100%
Generator Woman's affairs | 0 | 0 | 42S XD 098354 | Generator Woman's affairs | CERP | Laghman | Complete | 100%
Police Tents/Generators/ Gates | 0 | 0 | 42S XD 098354 | Police Tents/Generators/ Gates | CERP | Laghman | Complete | 100%
Police jail/ arms room | 0 | 0 | 42S XD 098354 | Police jail/ arms room | CERP | Nangarhar | Cancel? Other funding | 0%
HA Tents & blankets for DCs | 0 | 0 | 42S XD 1044 3744 | HA Tents & blankets for DCs | CERP | Laghman | Complete | 100%
Ambulance | 0 | 0 | 42S XD 1045 3744 | Ambulance | CERP | Laghman | Complete | 100%
Move the mountain | 0 | 0 | 42S XD 1045 3744 | Move the mountain | CERP | Laghman | Complete | 100%
Porch for eye clinic | 0 | 0 | 42S XD 1045 3744 | Porch for eye clinic | CERP | Laghman | Complete | 100%
Karotometer for Clinic | 0 | 0 | 42S XD 1045 3744 | Karotometer for Clinic | CERP | Laghman | Complete | 100%
Mehtar Lam Hospital Optical Center | 0 | 0 | 42S XD 10483 37375 | Mehtar Lam Hospital Optical Center | OHDACA | Laghman | Complete | 80%
Flying Coach Van (TV Radio) | 0 | 0 | 42S XD 1062 3631 | Flying Coach Van (TV Radio) | CERP | Nangarhar | locate vehicle | 0%
Cultural Kitchen | 0 | 0 | 42S XD 1067 3620 | Cultural Kitchen | CERP | Nangarhar | Complete | 100%
Police Motorcycles for Laghman Province | 0 | 0 | 42S XD 1070 3600 | Police Motorcycles for Laghman Province | CERP | Laghman | Complete | 100%
Radio Air Time | 0 | 0 | 42S XD 1070 3600 | Radio Air Time | CERP | Nangarhar | QA/QC | 50%
Supplies/Transportation for Mullah conference | 0 | 0 | 42S XD 1070 3600 | Supplies/Transportation for Mullah conference | CERP | Nangarhar | Complete | 100%
Generator Jalalabad Jail | 0 | 0 | 42S XD 1070 3600 | Generator Jalalabad Jail | CERP | Nangarhar | Complete | 100%
Refridgerators for clinics | 0 | 0 | 42S XD 1070 3600 | Refridgerators for clinics | CERP | Nangarhar | Complete | 100%
Police Patrol Trucks | 0 | 0 | 42S XD 1070 3600 | Police Patrol Trucks | CERP | Nangarhar | Complete | 100%
Sheets & bedding for Jail | 0 | 0 | 42S XD 1070 3600 | Sheets & bedding for Jail | CERP | Nangarhar | Complete | 100%
Retro-Fit Police Vehicle | 0 | 0 | 42S XD 1070 3600 | Retro-Fit Police Vehicle | CERP | Nangarhar | Complete | 0%
Dairy Farm | 0 | 0 | 42S XD 1070 3600 | Dairy Farm | CERP | Nangarhar | Awaiting Estimate | 0%
Ambulance- UH | 0 | 0 | 42S XD 1070 3600 | Ambulance- UH | CERP | Nangarhar | locate vehicle | 0%
Police detainee transport vehicle | 0 | 0 | 42S XD 1070 3600 | Police detainee transport vehicle | CERP | Nangarhar | locate vehicle | 0%
Hygene/ plumbing for Jail | 0 | 0 | 42S XD 1070 3600 | Hygene/ plumbing for Jail | CERP | Nangarhar | Write Contract | 0%
Vet Drugs/ surgical equipment | 0 | 0 | 42S XD 1073 3635 | Vet Drugs/ surgical equipment | CERP | Nangarhar | Complete | 100%
HA Distro to poor families | 0 | 0 | 42S XD 140 256 | HA Distro to poor families | CMO | Nangarhar | Complete | 100%
Shamshapure Village Wells | 0 | 0 | 42S XD 1707 0906 | Shamshapure Village Wells | OHDACA | Nangarhar |  | 0%
School in Gari Khale | 0 | 0 | 42S XD 180 850 | School in Gari Khale | OHDACA | Nangarhar |  | 0
Surkh Rod District School Desks | 0 | 0 | 42S XD 215 092 | Surkh Rod District School Desks | OHDACA | Nangarhar | Complete | 100%
Sultan Pure Girls School | 0 | 0 | 42S XD 21636 09135 | Sultan Pure Girls School | OHDACA | Nangarhar | Complete | 100%
Bandeh Azim village wells | 0 | 0 | 42S XD 231 087 | Bandeh Azim village wells | OHDACA | Nangarhar | Complete | 100%
Alingar Girls School | 0 | 0 | 42S XD 241 541 | Alingar Girls School | CERP | Laghman | Complete | 90%
Maziri Road | 0 | 0 | 42S XD 245 457 | Maziri Road | CERP | Laghman | Pending Approval | 0%
Kundagal Road | 0 | 0 | 42S XD 245 457 | Kundagal Road | CERP | Laghman | Pending Approval | 0%
Micro-Hydro | 0 | 0 | 42S XD 245 547 | Micro-Hydro | CERP | Laghman | Pending Approval | 0%
Ambulance | 0 | 0 | 42S XD 245 550 | Ambulance | CERP | Laghman | Complete | 100%
Teacher supplies | 0 | 0 | 42S XD 245 550 | Teacher supplies | CERP | Laghman | Complete | 100%
Lights/ Fans for Clinic | 0 | 0 | 42S XD 245 550 | Lights/ Fans for Clinic | CERP | Laghman | Complete | 100%
Qalatek Co-Ed High School | 0 | 0 | 42S XD 245 550 | Qalatek Co-Ed High School | OHDACA | Laghman | Pending Approval | 0%
Woman's Dorm at clinic | 0 | 0 | 42S XD 245 550 | Woman's Dorm at clinic | CERP | Laghman | QA/QC | 70%
High Voltage Power Cable | 0 | 0 | 42S XD 24821686 | High Voltage Power Cable | CERP | Nangarhar | Complete | 100%
Jalalabad School Desks | 0 | 0 | 42S XD 25684 11123 | Jalalabad School Desks | OHDACA | Nangarhar | Complete | 100%
Tool package for PW dept | 0 | 0 | 42S XD 293 782 | Tool package for PW dept | CERP | Nuristan | Complete | 100%
Road repair Tool pkg for District | 0 | 0 | 42S XD 293 782 | Road repair Tool pkg for District | CERP | Nuristan | Complete | 0%
Public Works Pkg for Doab | 0 | 0 | 42S XD 293 782 | Public Works Pkg for Doab | CERP | Nuristan | Complete | 100%
Police Head Quarters | 0 | 0 | 42S XD 293 782 | Police Head Quarters | OHDACA | Nuristan | Pending Approval | 0%
Joe Haft Well #1 & #2 | 0 | 0 | 42S XD 31347 09762 | Joe Haft Well #1 & #2 | OHDACA | Nangarhar | Complete | 100%
Repair police station police | 0 | 0 | 42S XD 3140 1180 | Repair police station police | CERP | Nangarhar | Complete | 100%
Jalalabad (Chaknawury) Boy's Secondary and High School | 0 | 0 | 42S XD 31575 11246 | Jalalabad (Chaknawury) Boy's Secondary and High School | OHDACA | Nangarhar | Complete | 100%
Woman's Affairs Park | 0 | 0 | 42S XD 316 107 | Woman's Affairs Park | CERP | Nangarhar | Complete | 100%
Guard Post at Woman's Affairs | 0 | 0 | 42S XD 316 107 | Guard Post at Woman's Affairs | CERP | Nangarhar | Complete | 0%
Gate Repair | 0 | 0 | 42S XD 3160 1153 | Gate Repair | CERP | Nangarhar | Complete | 100%
Motorcycles for Nangarhar DC | 0 | 0 | 42S XD 3165 1170 | Motorcycles for Nangarhar DC | CERP | Nangarhar | Complete | 100%
Police Trucks III-Kunor | 0 | 0 | 42S XD 318 117 | Police Trucks III-Kunor | CERP | Nangarhar | QA/QC | 0%
Polling Site QRF Tents | 0 | 0 | 42S XD 318 117 | Polling Site QRF Tents | CERP | Nangarhar | Complete | 0%
Jalalabad Bus Station | 0 | 0 | 42S XD 318 117 | Jalalabad Bus Station | CERP | Nangarhar | Pending Approval | 0%
Addition to Girls School (Naswan) | 0 | 0 | 42S XD 3182 1172 | Addition to Girls School (Naswan) | CERP | Nangarhar | Complete | 100%
Police Emergency Response Vehicle- Bus | 0 | 0 | 42S XD 3182 1172 | Police Emergency Response Vehicle- Bus | CERP | Nangarhar | Complete | 100%
Jalalabad (Naswan) Girl's Secondary and High School | 0 | 0 | 42S XD 3182 1172 | Jalalabad (Naswan) Girl's Secondary and High School | OHDACA | Nangarhar | Complete | 100%
Pachir Agam Clinic Package | 0 | 0 | 42S XD 3182 1172 | Pachir Agam Clinic Package | CERP | Nangarhar | Complete | 100%
Repair for Pachir Agam Clinic | 0 | 0 | 42S XD 3182 1172 | Repair for Pachir Agam Clinic | CERP | Nangarhar | Complete | 100%
Ambulance | 0 | 0 | 42S XD 3182 1172 | Ambulance | CERP | Nangarhar | locate vehicle | 0%
Police motorcycles I - Jbad | 0 | 0 | 42S XD 3182 1173 | Police motorcycles I - Jbad | CERP | Nangarhar | Complete | 100%
Tents and Generators for Police | 0 | 0 | 42S XD 3182 1173 | Tents and Generators for Police | CERP | Nangarhar | Complete | 100%
Police substation | 0 | 0 | 42S XD 3182 1174 | Police substation | CERP | Nangarhar | Pending Approval | 0%
Joehaft Park | 0 | 0 | 42S XD 3182 1175 | Joehaft Park | CERP | Nangarhar | Complete | 100%
Naswan Park | 0 | 0 | 42S XD 3182 1176 | Naswan Park | CERP | Nangarhar | Complete | 100%
Generator/ Police Station | 0 | 0 | 42S XD 3200 1175 | Generator/ Police Station | CERP | Nangarhar | Complete | 100%
Police SUV | 0 | 0 | 42S XD 3200 1175 | Police SUV | CERP | Nangarhar | Complete | 100%
PHH GarbageTruck / SewageTruck | 0 | 0 | 42S XD 32072 11635 | PHH GarbageTruck / SewageTruck | CERP | Nangarhar | QA/QC | 50%
Refurbish OBGYN Clinic | 0 | 0 | 42S XD 32072 11635 | Refurbish OBGYN Clinic | CERP | Nangarhar | Complete | 100%
Jalalabad Public Health Hospital | 0 | 0 | 42S XD 32072 11635 | Jalalabad Public Health Hospital | OHDACA | Nangarhar | Complete | 90%
Infrastructure for Midwife Training Center | 0 | 0 | 42S XD 32072 11635 | Infrastructure for Midwife Training Center | USAID | Nangarhar | QA/QC | 50%
Ambulance- PHH | 0 | 0 | 42S XD 32072 11635 | Ambulance- PHH | CERP | Nangarhar | locate vehicle | 0%
HA Distro to DF Camp | 0 | 0 | 42S XD 32377 11437 | HA Distro to DF Camp | CMO | Nangarhar | Complete | 100%
Moushko Khan School Desks | 0 | 0 | 42S XD 333433 097222 | Moushko Khan School Desks | OHDACA | Nangarhar | Complete | 100%
School desk delivery | 0 | 0 | 42S XD 3400 1000 | School desk delivery | CERP | Nangarhar | Complete | 100%
School desk delivery II | 0 | 0 | 42S XD 3400 1000 | School desk delivery II | CERP | Nangarhar | Complete | 100%
Nangarhar University Training Hospital | 0 | 0 | 42S XD 349 106 | Nangarhar University Training Hospital | OHDACA | Nangarhar | Complete | 100%
Agricultural and Technical High School | 0 | 0 | 42S XD 3495 0969 | Agricultural and Technical High School | OHDACA | Nangarhar | Complete | 100%
Bebe Aieshe Sediqa Girls School | 0 | 0 | 42S XD 3495 1068 | Bebe Aieshe Sediqa Girls School | OHDACA | Nangarhar |  | 97%
Safe house Park | 0 | 0 | 42S XD 3500 1040 | Safe house Park | CERP | Nangarhar | Complete | 100%
Abdu Rahim Niazi Primary School | 0 | 0 | 42S XD 365 103 | Abdu Rahim Niazi Primary School | OHDACA | Nangarhar |  | 0%
Desks/ School Supplies | 0 | 0 | 42S XD 370 080 | Desks/ School Supplies | CERP | Nangarhar | Complete | 100%
Breaker Box/Wire/ Fans for Clinic | 0 | 0 | 42S XD 370 080 | Breaker Box/Wire/ Fans for Clinic | CERP | Nangarhar | Complete | 100%
Customs Water System | 0 | 0 | 42S XD 370 080 | Customs Water System | CERP | Nangarhar | Complete | 100%
Community/student cleanup | 0 | 0 | 42S XD 370 080 | Community/student cleanup | CERP | Nangarhar | Complete | 100%
Culture/ press center | 0 | 0 | 42S XD 370 080 | Culture/ press center | CERP | Nangarhar | Complete | 100%
Referbish the Airport | 0 | 0 | 42S XD 378 078 | Referbish the Airport | OHDACA | Nangarhar |  | 0
Refurbish Airport Fire Truck | 0 | 0 | 42S XD 398 067 | Refurbish Airport Fire Truck | CERP | Nangarhar | Complete | 100%
Shergar Village Wells | 0 | 0 | 42S XD 47366 13812 | Shergar Village Wells | OHDACA | Nangarhar | Complete | 100%
Repair culverts | 0 | 0 | 42S XD 4970 0830 | Repair culverts | CERP | Nangarhar | Complete | 100%
Kando School | 0 | 0 | 42S XD 4970 0830 | Kando School | CERP | Nangarhar | Complete | 100%
Generator for health clinic | 0 | 0 | 42S XD 4970 0830 | Generator for health clinic | CERP | Nangarhar | Complete | 100%
Ambulance | 0 | 0 | 42S XD 4970 0830 | Ambulance | CERP | Nangarhar | Complete | 100%
Culvert repair II | 0 | 0 | 42S XD 4970 0830 | Culvert repair II | CERP | Nangarhar | Complete | 100%
Lights/ Fans for Clinic | 0 | 0 | 42S XD 4970 0830 | Lights/ Fans for Clinic | CERP | Nangarhar | Complete | 100%
Micro-Hydro | 0 | 0 | 42S XD 4970 0830 | Micro-Hydro | CERP | Nangarhar | Complete | 95%
Meshwani Elementary School | 0 | 0 | 42S XD 58715 01680 | Meshwani Elementary School | OHDACA | Nangarhar | Complete | 95%
Meshwani Village Wells | 0 | 0 | 42S XD 595 010 | Meshwani Village Wells | OHDACA | Nangarhar | Complete | 0%
Generator for health clinic | 0 | 0 | 42S XD 630 028 | Generator for health clinic | CERP | Nangarhar | Complete | 100%
Ambulance | 0 | 0 | 42S XD 630 028 | Ambulance | CERP | Nangarhar | Complete | 100%
Lights/ Fans for Clinic | 0 | 0 | 42S XD 630 028 | Lights/ Fans for Clinic | CERP | Nangarhar | Complete | 100%
Doral khel Awal Co-Ed Primary School | 0 | 0 | 42S XD 7200 0875 | Doral khel Awal Co-Ed Primary School | CERP | Nangarhar | Pending Approval | 0%
Zyarat Co-Ed Primary School | 0 | 0 | 42S XD 7517 7183 | Zyarat Co-Ed Primary School | OHDACA | Nangarhar | Pending Approval | 0%
Micro-Hydro | 0 | 0 | 42S XD 982 681 | Micro-Hydro | CERP | Laghman | Pending Approval | 0%
Generator for health clinic | 0 | 0 | 42S XD245 550 | Generator for health clinic | CERP | Laghman | Complete | 100%
Tool Package for PW Dept. | 0 | 0 | 42S XD245 550 | Tool Package for PW Dept. | CERP | Laghman | Complete | 100%
Generator for health clinic | 0 | 0 | 42S XW 978 682 | Generator for health clinic | CERP | Laghman | Complete | 100%
Ambulance | 0 | 0 | 42S XW 978 682 | Ambulance | CERP | Laghman | Complete | 100%
Lights/ Fans for Clinic | 0 | 0 | 42S XW 978 682 | Lights/ Fans for Clinic | CERP | Laghman | Complete | 100%
Batsawul School Desks | 0 | 0 | 42SXC 73305 90778 | Batsawul School Desks | OHDACA | Nangarhar | Complete | 100%
Shahi Kot Secondary School | 0 | 0 | 42SXC44660 93094 | Shahi Kot Secondary School | OHDACA | Nangarhar | Complete | 100%
Shinwar Loya Girl's School | 0 | 0 | 42SXC855655 | Shinwar Loya Girl's School | CERP | Nangarhar | Complete | 100%
Chapahar District Rotary School Desks | 0 | 0 | 42SXD 31483 03478 | Chapahar District Rotary School Desks | OHDACA | Nangarhar | Complete | 100%
Charbaghe High School Desks | 0 | 0 | 42SXD26952 11373 | Charbaghe High School Desks | OHDACA | Nangarhar | Complete | 100%
Abdu Rahim Niazi Primary School | 0 | 0 | 42SXD3650010300 | Abdu Rahim Niazi Primary School | CERP | Nangarhar | Complete | 100%
Tariq Primary School | 0 | 0 | 42X WD 06614062 | Tariq Primary School | CERP | Laghman | Complete | 95%
Zarkamar Primary School | 0 | 0 | 42X WD 965690 | Zarkamar Primary School | CERP | Laghman | QA/QC | 10%
Dawlet Shaw Primary School | 0 | 0 | 42X WD 97556950 | Dawlet Shaw Primary School | CERP | Laghman | QA/QC | 70%
Rehab Gadyalai School | 0 | 0 | WD 944 695 | Rehab Gadyalai School | USAID | Laghman | Complete | 100%
Dawlat Shah District Government Center | 0 | 0 | WD 975 690 | Dawlat Shah District Government Center | USAID | Laghman | QA/QC | 6%
Dawlet Shaw Health Clinic | 0 | 0 | WD 975 695 | Dawlet Shaw Health Clinic | OHDACA | Laghman | Pending Approval | 0%
New Khogyani Basic Clinic | 0 | 0 | XC 010 968 | New Khogyani Basic Clinic | USAID | Nangarhar | QA/QC | 60%
Pave Kagha District Center | 0 | 0 | XC 095 910 | Pave Kagha District Center | USAID | Nangarhar | QA/QC | 5%
New Chaparhar Basic Clinic | 0 | 0 | XC 210 900 | New Chaparhar Basic Clinic | USAID | Nangarhar | QA/QC | 85%
Pave Chaparhar District Center | 0 | 0 | XC 250 935 | Pave Chaparhar District Center | USAID | Nangarhar | QA/QC | 15%
Kagha Village Piped Water Supply | 0 | 0 | XC 250 935 | Kagha Village Piped Water Supply | USAID | Nangarhar | Design | 0%
Chaparhar District Government Center | 0 | 0 | XC 253 938 | Chaparhar District Government Center | USAID | Nangarhar | QA/QC | 40%
Chaparhar Village Bazaar Piped Water Supply | 0 | 0 | XC 253 938 | Chaparhar Village Bazaar Piped Water Supply | USAID | Nangarhar | Sending BOQ | 18%
Ghenikhel Village Piped Water System | 0 | 0 | XC 656 859 | Ghenikhel Village Piped Water System | USAID | Nangarhar | QA/QC | 40%
Muhmand Dara Community Center | 0 | 0 | XC 731 907 | Muhmand Dara Community Center | USAID | Nangarhar | Complete | 100%
Alishing District Government Center | 0 | 0 | XD 010 511 | Alishing District Government Center | USAID | Laghman | QA/QC | 28%
Alishing District Bazaar Protection Wall | 0 | 0 | XD 012 498 | Alishing District Bazaar Protection Wall | USAID | Laghman | QA/QC | 99%
Rehab Qal'eh-ye Najiel School | 0 | 0 | XD 018 613 | Rehab Qal'eh-ye Najiel School | USAID | Laghman | Complete | 100%
New Qarghayi Basic Clinic | 0 | 0 | XD 112 264 | New Qarghayi Basic Clinic | USAID | Laghman | QA/QC | 80%
Shamshapur Causway | 0 | 0 | XD 251 093 | Shamshapur Causway | USAID | Nangarhar | QA/QC | 45%
Shamshapur Road Improvement | 0 | 0 | XD 251 093 | Shamshapur Road Improvement | USAID | Nangarhar | QA/QC | 68%
Shamshapur/Sultanpur River Canalizing | 0 | 0 | XD 251 093 | Shamshapur/Sultanpur River Canalizing | USAID | Nangarhar | QA/QC | 80%
Women's Affairs Center | 0 | 0 | XD 316 107 | Women's Affairs Center | USAID | Nangarhar | Complete | 100%
Pave Jalalabad to Asmar Road 0 - 10 KM | 0 | 0 | XD 342 126 | Pave Jalalabad to Asmar Road 0 - 10 KM | USAID | Nangarhar | QA/QC | 25%
Rehab Qal'eh-ye Janan Khan School | 0 | 0 | XD 345 130 | Rehab Qal'eh-ye Janan Khan School | USAID | Nangarhar | Complete | 100%
Rehab Yasin Baba High School | 0 | 0 | XD 415 225 | Rehab Yasin Baba High School | USAID | Nangarhar | Complete | 100%
Kama Customs Facility | 0 | 0 | XD 431 149 | Kama Customs Facility | USAID | Nangarhar | QA/QC | 99%
New Kuz Kunar Basic Clinic | 0 | 0 | XD 431 230 | New Kuz Kunar Basic Clinic | USAID | Nangarhar | QA/QC | 75%
Construct Shegah Main Canal Intake | 0 | 0 | XD 440 230 | Construct Shegah Main Canal Intake | USAID | Nangarhar | QA/QC | 90%
Rehab Tokal Baba Girls School | 0 | 0 | XD 452 265 | Rehab Tokal Baba Girls School | USAID | Nangarhar | Complete | 100%
New Kama Basic Clinic | 0 | 0 | XD 470 120 | New Kama Basic Clinic | USAID | Nangarhar | QA/QC | 85%
New Machgandol School | 0 | 0 | XD 483 422 | New Machgandol School | USAID | Nangarhar | QA/QC | 25%
New Lal Mohammad Shaheed School | 0 | 0 | XD 502 285 | New Lal Mohammad Shaheed School | USAID | Nangarhar | QA/QC | 80%
Pave Kama District Center | 0 | 0 | XD 508 092 | Pave Kama District Center | USAID | Nangarhar | QA/QC | 10%
Kama Community Center | 0 | 0 | XD 508 092 | Kama Community Center | USAID | Nangarhar | Complete | 100%
Construction of Goushta District Gov't Bldg | 0 | 0 | XD 618 045 | Construction of Goushta District Gov't Bldg | USAID | Nangarhar | QA/QC | 68%
Goshta Customs Facility | 0 | 0 | XD 618 045 | Goshta Customs Facility | USAID | Nangarhar | QA/QC | 66%
Pave Jalalabad to Asmar Road 10 - 20 KM | 0 | 0 | XD420 160 | Pave Jalalabad to Asmar Road 10 - 20 KM | USAID | Nangarhar | QA/QC | 25%
Construction of district government Building | 0 | 0 | XD508 092 | Construction of district government Building | USAID | Nangarhar | QA/QC | 65%

## Projs No Coords
Police EOD Van & Trailer | 0 | 0 | Police EOD Van & Trailer | CERP | Nangarhar | Awaiting Estimate | 0%
One Day Women Seminar | 0 | 0 | One Day Women Seminar | USAID | Nangarhar | Complete | 100%
Pave Jalalabad to Asmar Road 20 - 30 KM | 0 | 0 | Pave Jalalabad to Asmar Road 20 - 30 KM | USAID | Nangarhar | QA/QC | 25%
Masjid Kartha Mamoreen Mosque | 0 | 0 | Masjid Kartha Mamoreen Mosque | CERP | Laghman
Moscura Retaining Wall | 0 | 0 | Moscura Retaining Wall | USAID | Laghman | Complete | 100%
One Day Women Seminar | 0 | 0 | One Day Women Seminar | USAID | Laghman | Complete | 100%
Accelerated Learning for Overage Kids | 0 | 0 | Accelerated Learning for Overage Kids | USAID | Laghman | M&E | 33%
Pave Mehterlam District Center | 0 | 0 | Pave Mehterlam District Center | USAID | Laghman | Design | 0%
Women's Affairs Center | 0 | 0 | Women's Affairs Center | USAID | Laghman | QA/QC | 99%
Textbook Distribution (865,169 books) | 0 | 0 | Textbook Distribution (865,169 books) | USAID | Laghman | WIP | 50%
Laghman State Radio Station | 0 | 0 | Laghman State Radio Station | USAID | Laghman | Procure | 25%
Equipment for AWDC Laghman | 0 | 0 | Equipment for AWDC Laghman | USAID | Laghman | Approval from Kabul | 60%
District Courthouse | 0 | 0 | District Courthouse | USAID | Laghman
Tents and Stoves | 0 | 0 | Tents and Stoves | CERP | Laghman
Pave Kahi District Center | 0 | 0 | Pave Kahi District Center | USAID | Nangarhar | QA/QC | 5%
Construct Farm to Mkt Rd from Gheni Khil Bazaar to Shergard to Shaw Kani (20KM) | 0 | 0 | Construct Farm to Mkt Rd from Gheni Khil Bazaar to Shergard to Shaw Kani (20KM) | USAID | Nangarhar | Design | 0%
Achin Community Center | 0 | 0 | Achin Community Center | USAID | Nangarhar | Complete | 100%
Shaheed Gul Primary School | 0 | 0 | Shaheed Gul Primary School | DOS | Nangarhar | Complete | 100%
School | 0 | 0 | School | DOS | Nangarhar | Complete | 100%
Mast Baba Primary School | 0 | 0 | Mast Baba Primary School | DOS | Nangarhar | Complete | 100%
Kai High School | 0 | 0 | Kai High School | DOS | Nangarhar | Complete | 100%
Construct Test Farm to Market Road Surtak to Dekphor & Saiphon to Kot (10KM total) | 0 | 0 | Construct Test Farm to Market Road Surtak to Dekphor & Saiphon to Kot (10KM total) | USAID | Nangarhar | QA/QC | 60%
Bati Kot Community Center | 0 | 0 | Bati Kot Community Center | USAID | Nangarhar | Complete | 100%
Bati Kot CHC | 0 | 0 | Bati Kot CHC | USAID | Nangarhar
Chardai Clinic | 0 | 0 | Chardai Clinic | USAID | Nangarhar
Kot High School | 0 | 0 | Kot High School | DOS | Nangarhar | Complete | 100%
Najmul Madaris | 0 | 0 | Najmul Madaris | USAID | Nangarhar
Baharabad Middle School | 0 | 0 | Baharabad Middle School | USAID | Nangarhar
Jui 11 Primary School | 0 | 0 | Jui 11 Primary School | DOS | Nangarhar | Complete | 100%
Kareez Kabir Clinic | 0 | 0 | Kareez Kabir Clinic | DOS | Nangarhar | Complete | 100%
Najm I Kura (Hada) Clinic | 0 | 0 | Najm I Kura (Hada) Clinic | DOS | Nangarhar | Complete | 100%
Baharabad Girls School | 0 | 0 | Baharabad Girls School | USAID | Nangarhar
Daulatzai Madrasa | 0 | 0 | Daulatzai Madrasa | DOS | Nangarhar | Complete | 100%
Lalma School | 0 | 0 | Lalma School | DOS | Nangarhar | Complete | 100%
Mander Khil Primary Sch | 0 | 0 | Mander Khil Primary Sch | DOS | Nangarhar | Complete | 100%
Manu Primary School | 0 | 0 | Manu Primary School | DOS | Nangarhar | Complete | 100%
Sangina Chaparhar Clinic | 0 | 0 | Sangina Chaparhar Clinic | DOS | Nangarhar | Complete | 100%
Trelei Clinic | 0 | 0 | Trelei Clinic | DOS | Nangarhar | Complete | 100%
Construct Farm to Mkt Rd from Jbad to Chaparhar to Agam (34KM) | 0 | 0 | Construct Farm to Mkt Rd from Jbad to Chaparhar to Agam (34KM) | USAID | Nangarhar | Design | 0%
Darae Noor High & Primary Schools | 0 | 0 | Darae Noor High & Primary Schools | USAID | Nangarhar
Haqania Darul Uloom | 0 | 0 | Haqania Darul Uloom | USAID | Nangarhar
Der Koat Girls Middle School | 0 | 0 | Der Koat Girls Middle School | USAID | Nangarhar
Dih Bala Dara Community Center | 0 | 0 | Dih Bala Dara Community Center | USAID | Nangarhar | Complete | 100%
Papeen High School | 0 | 0 | Papeen High School | USAID | Nangarhar
Peshawoli | 0 | 0 | Peshawoli | USAID | Nangarhar
Ghenikhel Community Center | 0 | 0 | Ghenikhel Community Center | USAID | Nangarhar | Complete | 100%
School | 0 | 0 | School | DOS | Nangarhar | Complete | 100%
Hisarak Village Wells | 0 | 0 | Hisarak Village Wells | OHDACA | Nangarhar | Complete
Hisarak Dara Community Center | 0 | 0 | Hisarak Dara Community Center | USAID | Nangarhar | Complete | 100%
Hizarek Medicines | 0 | 0 | Hizarek Medicines | CERP | Nangarhar
Refurbish Culture/Press center buildings | 0 | 0 | Refurbish Culture/Press center buildings | CERP | Nangarhar | Complete/pay out | 100%
Motorola Support | 0 | 0 | Motorola Support | CERP | Nangarhar | Purchase Generators | 90%
University Faculty of Veterinary Medicine Building | 0 | 0 | University Faculty of Veterinary Medicine Building | USAID | Nangarhar | QA/QC | 8%
Capacity building of MoPW,Jalalabad | 0 | 0 | Capacity building of MoPW,Jalalabad | USAID | Nangarhar | Complete | 100%
Repair of Irrigation Equipment | 0 | 0 | Repair of Irrigation Equipment | USAID | Nangarhar | Cancelled | 0
Capacity building Nangarhar Municipality #1 | 0 | 0 | Capacity building Nangarhar Municipality #1 | USAID | Nangarhar | QA/QC | 99%
Capacity Building Nangarhar Urban Development #1 | 0 | 0 | Capacity Building Nangarhar Urban Development #1 | USAID | Nangarhar | Complete | 99%
Jalalabad City Water Supply | 0 | 0 | Jalalabad City Water Supply | USAID | Nangarhar | Design
Women's Market | 0 | 0 | Women's Market | USAID | Nangarhar | Approval from Kabul | 0%
Capacity Building: MRRD | 0 | 0 | Capacity Building: MRRD | USAID | Nangarhar | Approval from Kabul | 0%
Accelerated Learning for Overage Kids | 0 | 0 | Accelerated Learning for Overage Kids | USAID | Nangarhar | M&E | 33%
Midwife Training Program | 0 | 0 | Midwife Training Program | USAID | Nangarhar | M&E
Rehab of 116KM of Blocked Drainage Ditches | 0 | 0 | Rehab of 116KM of Blocked Drainage Ditches | USAID | Nangarhar | QA/QC | 5%
Political Party Training | 0 | 0 | Political Party Training | USAID | Nangarhar | WIP
Textbook Distribution (1,535,472 books) | 0 | 0 | Textbook Distribution (1,535,472 books) | USAID | Nangarhar | WIP | 50%
Rehab 60KM of Canal & Jui's 11 thru 28 | 0 | 0 | Rehab 60KM of Canal & Jui's 11 thru 28 | USAID | Nangarhar | Complete | 100%
Mujadela-e-Malaria Center | 0 | 0 | Mujadela-e-Malaria Center | USAID | Nangarhar
Sehat Ravani Clinic | 0 | 0 | Sehat Ravani Clinic | USAID | Nangarhar
A. Wakil Middle School | 0 | 0 | A. Wakil Middle School | USAID | Nangarhar
NGR Center High School | 0 | 0 | NGR Center High School | USAID | Nangarhar
Womens Clothing | 0 | 0 | Womens Clothing | CERP | Nangarhar
Spin Mosque | 0 | 0 | Spin Mosque | CERP | Nangarhar
Eastern Region Governors Conference | 0 | 0 | Eastern Region Governors Conference | CERP | Nangarhar
Zangobaya Medcap | 0 | 0 | Zangobaya Medcap | CERP | Nangarhar
Tribal Affairs Repair | 0 | 0 | Tribal Affairs Repair | CERP | Nangarhar
Zor Qasaba Electric | 0 | 0 | Zor Qasaba Electric | CERP | Nangarhar
CMOC | 0 | 0 | CMOC | CERP | Nangarhar | QA/QC | 30%
Force Pro Wall | 0 | 0 | Force Pro Wall | CERP | Nangarhar | Complete | 100%
Renovation of Hotel & DFAC | 0 | 0 | Renovation of Hotel & DFAC | CERP | Nangarhar | Complete | 100%
Afghan Billets Latrine Renovation | 0 | 0 | Afghan Billets Latrine Renovation | CERP | Nangarhar | Complete | 100%
Medical & Laundry Facility | 0 | 0 | Medical & Laundry Facility | CERP | Nangarhar | Complete | 100%
Admin Building | 0 | 0 | Admin Building | CERP | Nangarhar | Complete | 100%
Maintenance Building | 0 | 0 | Maintenance Building | CERP | Nangarhar | Complete | 100%
Surge Well | 0 | 0 | Surge Well | CERP | Nangarhar | Complete | 100%
Surge Force Billeting | 0 | 0 | Surge Force Billeting | CERP | Nangarhar | Complete | 30%
Force Pro Wall Upgrade | 0 | 0 | Force Pro Wall Upgrade | CERP | Nangarhar | Complete | 100%
Cinema Latrine | 0 | 0 | Cinema Latrine | CERP | Nangarhar | Complete | 100%
Power Generation | 0 | 0 | Power Generation | CERP | Nangarhar | Complete | 100%
Helipad | 0 | 0 | Helipad | CERP | Nangarhar | Complete | 100%
Construct Test Farm to Market Road from Kama to Goushta (10KM) | 0 | 0 | Construct Test Farm to Market Road from Kama to Goushta (10KM) | USAID | Nangarhar | QA/QC | 90%
Construct Farm to Mkt Rd from Kama to Goushta (Last 9KM) | 0 | 0 | Construct Farm to Mkt Rd from Kama to Goushta (Last 9KM) | USAID | Nangarhar | Design | 0%
Baghicha High School | 0 | 0 | Baghicha High School | DOS | Nangarhar | Complete | 100%
Darga Primary School | 0 | 0 | Darga Primary School | DOS | Nangarhar | Complete | 100%
Nimla School | 0 | 0 | Nimla School | DOS | Nangarhar | Complete | 100%
Piera Khil Primary School | 0 | 0 | Piera Khil Primary School | DOS | Nangarhar | Complete | 100%
Construct Farm to Mkt Rd from Kaga to Saraka to Kager (12KM) | 0 | 0 | Construct Farm to Mkt Rd from Kaga to Saraka to Kager (12KM) | USAID | Nangarhar | Design | 0%
Construct Farm to Mkt Rd from Kaga to Mama Khil (33KM) | 0 | 0 | Construct Farm to Mkt Rd from Kaga to Mama Khil (33KM) | USAID | Nangarhar | Design | 0%
Khogyani Community Center | 0 | 0 | Khogyani Community Center | USAID | Nangarhar | Complete | 100%
Construct Karm Khiel Country Stores (3 each) | 0 | 0 | Construct Karm Khiel Country Stores (3 each) | USAID | Nangarhar | Complete | 100%
Gaga Girls Middle School | 0 | 0 | Gaga Girls Middle School | USAID | Nangarhar
Hashim Khel Middle School | 0 | 0 | Hashim Khel Middle School | USAID | Nangarhar
Construct Koti Tarn Canal Wasteways & Intakes | 0 | 0 | Construct Koti Tarn Canal Wasteways & Intakes | USAID | Nangarhar | QA/QC | 80%
Construct Kachar Canal Wasteways & Intakes | 0 | 0 | Construct Kachar Canal Wasteways & Intakes | USAID | Nangarhar | QA/QC | 80%
Shewa Community Center | 0 | 0 | Shewa Community Center | USAID | Nangarhar | Complete | 100%
Kuz Kunar Clinic | 0 | 0 | Kuz Kunar Clinic | USAID | Nangarhar
Tawkal Baba High School | 0 | 0 | Tawkal Baba High School | USAID | Nangarhar
Lal Poora CHC | 0 | 0 | Lal Poora CHC | USAID | Nangarhar
Toot Middle School | 0 | 0 | Toot Middle School | USAID | Nangarhar
Construct Farm to Mkt Rd from Hwy 1 to Canal 28 (7KM) | 0 | 0 | Construct Farm to Mkt Rd from Hwy 1 to Canal 28 (7KM) | USAID | Nangarhar | Design | 0%
Gardi Ghaws High School | 0 | 0 | Gardi Ghaws High School | USAID | Nangarhar
Nangarhar Civic Education Program | 0 | 0 | Nangarhar Civic Education Program | USAID | Nangarhar | Complete | 100%
Creating & Restooring Alternative Livelihoods (CRALS) I | 0 | 0 | Creating & Restooring Alternative Livelihoods (CRALS) I | DOS | Nangarhar | Complete | 100%
Creating & Restooring Alternative Livelihoods (CRALS) II | 0 | 0 | Creating & Restooring Alternative Livelihoods (CRALS) II | DOS | Nangarhar | QA/QC | 75%
Creating & Restooring Alternative Livelihoods (CRALS) III | 0 | 0 | Creating & Restooring Alternative Livelihoods (CRALS) III | DOS | Nangarhar | Design
Nazian Community Center | 0 | 0 | Nazian Community Center | USAID | Nangarhar | Complete | 100%
Agam Girls Primary School | 0 | 0 | Agam Girls Primary School | DOS | Nangarhar | Complete | 100%
Ag Marketing Cooperative Cold Storage Facility | 0 | 0 | Ag Marketing Cooperative Cold Storage Facility | USAID | Nangarhar | Procure | 0%
Jabeh Clinic | 0 | 0 | Jabeh Clinic | DOS | Nangarhar | Complete | 100%
Roghano Primary School | 0 | 0 | Roghano Primary School | DOS | Nangarhar | Complete | 100%
Pave Shershai District Center | 0 | 0 | Pave Shershai District Center | USAID | Nangarhar | Award | 0%
Construct Farm to Mkt Rd from Hwy 1 to Shahi Kot (8KM) | 0 | 0 | Construct Farm to Mkt Rd from Hwy 1 to Shahi Kot (8KM) | USAID | Nangarhar | Design | 0%
Construct Farm to Mkt Rd from Saiphon to Lagarjoi (20KM after test rd) | 0 | 0 | Construct Farm to Mkt Rd from Saiphon to Lagarjoi (20KM after test rd) | USAID | Nangarhar | WIP | 0%
Hisarak High School | 0 | 0 | Hisarak High School | USAID | Nangarhar
Potato Seed Distro & Tech Assist | 0 | 0 | Potato Seed Distro & Tech Assist | USAID | Nangarhar | QA/QC
Village Seed Enterprise Prgm | 0 | 0 | Village Seed Enterprise Prgm | USAID | Nangarhar | QA/QC
Crop Demo - Best Practices Project | 0 | 0 | Crop Demo - Best Practices Project | USAID | Nangarhar | QA/QC
Intro Protected Ag in Marginal & Water Deficient Areas | 0 | 0 | Intro Protected Ag in Marginal & Water Deficient Areas | USAID | Nangarhar | QA/QC
Agri-Input Trng & Dev Project | 0 | 0 | Agri-Input Trng & Dev Project | USAID | Nangarhar | QA/QC
Grape Revitalize for Afghan Productivity & Empowerment | 0 | 0 | Grape Revitalize for Afghan Productivity & Empowerment | USAID | Nangarhar | QA/QC
Emergency HA Relief - Blankets | 0 | 0 | Emergency HA Relief - Blankets | CERP | Nangarhar
Security Package Phase I | 0 | 0 | Security Package Phase I | CERP | Nangarhar
Markikhel Clinic | 0 | 0 | Markikhel Clinic | DOS | Nangarhar | Complete | 100%
Pettaow Primary School | 0 | 0 | Pettaow Primary School | DOS | Nangarhar | Complete | 100%
Tutu Primary School | 0 | 0 | Tutu Primary School | DOS | Nangarhar | Complete | 100%
Tutu High School | 0 | 0 | Tutu High School | DOS | Nangarhar | Complete | 100%
Gandumak Primary School | 0 | 0 | Gandumak Primary School | USAID | Nangarhar
Road from Marko Village to Ghenikhel Village | 0 | 0 | Road from Marko Village to Ghenikhel Village | USAID | Nangarhar | WIP | n/a
GheniKhel Daga Primary School | 0 | 0 | GheniKhel Daga Primary School | DOS | Nangarhar | Complete | 100%
Jui 28 Primary School | 0 | 0 | Jui 28 Primary School | DOS | Nangarhar | Complete | 100%
Marko Primary School | 0 | 0 | Marko Primary School | DOS | Nangarhar | Complete | 100%
Rehab Irrigation Canal & Protect from Flood | 0 | 0 | Rehab Irrigation Canal & Protect from Flood | USAID | Nangarhar | QA/QC | 70%
Construct Farm to Mkt Rd from Gheni Khil Hosp to Bazaar (3KM) | 0 | 0 | Construct Farm to Mkt Rd from Gheni Khil Hosp to Bazaar (3KM) | USAID | Nangarhar | Design | 0%
Kuz Kakarak Middle School | 0 | 0 | Kuz Kakarak Middle School | DOS | Nangarhar | Complete | 100%
Nabo Kala Clinic | 0 | 0 | Nabo Kala Clinic | DOS | Nangarhar | Complete | 100%
Shamshapur Clinic | 0 | 0 | Shamshapur Clinic | DOS | Nangarhar | Complete | 100%
Shamshapur Middle School | 0 | 0 | Shamshapur Middle School | DOS | Nangarhar | Complete | 100%
Sultanpur Aulia Middle School | 0 | 0 | Sultanpur Aulia Middle School | DOS | Nangarhar | Complete | 100%
Baghtan Clinic | 0 | 0 | Baghtan Clinic | DOS | Nangarhar | Complete | 100%
Fatehabad Primary School | 0 | 0 | Fatehabad Primary School | DOS | Nangarhar | Complete | 100%
Fatehabad Clinic | 0 | 0 | Fatehabad Clinic | DOS | Nangarhar | Complete | 100%
Construct Farm to Mkt Rd from Dend to Dusarak (4KM) | 0 | 0 | Construct Farm to Mkt Rd from Dend to Dusarak (4KM) | USAID | Nangarhar | Design | 0%
Surkh Rod Community Center | 0 | 0 | Surkh Rod Community Center | USAID | Nangarhar | Complete | 100%
Fatehabad Clinic | 0 | 0 | Fatehabad Clinic | USAID | Nangarhar
Kankran BHC | 0 | 0 | Kankran BHC | USAID | Nangarhar
Kakrak Middle School | 0 | 0 | Kakrak Middle School | USAID | Nangarhar
Balabagh Girls Middle School | 0 | 0 | Balabagh Girls Middle School | USAID | Nangarhar
Fatehabad Boys & Girls School | 0 | 0 | Fatehabad Boys & Girls School | USAID | Nangarhar
Shiwah Village Wells | 0 | 0 | Shiwah Village Wells | OHDACA | Nangarhar | Complete
Nuristan Meds | 0 | 0 | Nuristan Meds | CERP | Nuristan
Apple Orchards | 0 | 0 | Apple Orchards | CERP | Nuristan
Construct Greenhouse | 0 | 0 | Construct Greenhouse | USAID |  | WIP
Repair Bander Primary School | 0 | 0 | Repair Bander Primary School | OHDACA |  | Complete
Gombadi Mosque | 0 | 0 | Gombadi Mosque | CERP
Sheik Khali Mosque | 0 | 0 | Sheik Khali Mosque | CERP
Darunta Dam Mech/Elect Parts | 0 | 0 | Darunta Dam Mech/Elect Parts | CERP
PHH Hospital Mattresses | 0 | 0 | PHH Hospital Mattresses | CERP
Merkhani Clinic Retaining Wall | 0 | 0 | Merkhani Clinic Retaining Wall | CERP
Landikhel School Extension | 0 | 0 | Landikhel School Extension | CERP
Cistern Refurbishment | 0 | 0 | Cistern Refurbishment | CERP
| 0 | 0 |  | CERP
Chair/Desk Repair | 0 | 0 | Chair/Desk Repair | CERP
Repair Naswan and Chawkwanury Schools | 0 | 0 | Repair Naswan and Chawkwanury Schools | CERP
Prison Water Tank | 0 | 0 | Prison Water Tank | CERP
Electical Cables | 0 | 0 | Electical Cables | CERP
Public Health Hospital Intercom | 0 | 0 | Public Health Hospital Intercom | CERP
Prison Water Tank, Flash Light, Spot Light | 0 | 0 | Prison Water Tank, Flash Light, Spot Light | CERP
Kharoty Micro Hydro | 0 | 0 | Kharoty Micro Hydro | CERP
Pave Ghenikhel District Center | 0 | 0 | Pave Ghenikhel District Center | USAID | Nangarhar | QA/QC | 25%
Electric System | 0 | 0 | Electric System | USAID | Laghman | Need more research | 0%
Women's Civic Education | 0 | 0 | Women's Civic Education | USAID | Nangarhar | Complete | 100%
PABX Emergency Response System | 0 | 0 | PABX Emergency Response System | USAID | Nangarhar | Procure | 0%
Distro of Police Uniforms | 0 | 0 | Distro of Police Uniforms | CMO | Laghman | Complete | 100%
HA Distro to Imam Al Bukhari Widows Group | 0 | 0 | HA Distro to Imam Al Bukhari Widows Group | CMO | Nangarhar | Complete | 100%
HA Distro to Imam Al Bukhari Orphanage | 0 | 0 | HA Distro to Imam Al Bukhari Orphanage | CMO | Nangarhar | Complete | 100%
Distro of Police Uniforms | 0 | 0 | Distro of Police Uniforms | CMO | Nangarhar | Complete | 100%